## Project Master data
Projects Codes | Project/Initiatives Name | Project Description | LGA | Name of MDA | IS Column E a Ministry/ Department/ Agency/ Office? | Who is Column E reporting to? | MDA/LGA Weighting | State Weighting | Theme | Theme weighting | SDG | SDG weighting | Start Date | End Date | Timeline | Status | Budgetted Cost | Project Cost | Spent till date | Project Progress | IGR Projects | Specify the IGR status | Programs | IS THIS PROJECT PART OF AN INITIATIVE.? | SPECIFY THE TYPE OF INITIATIVE
SPDO-BLS-P-23-00010 | Production of all Maps of Chiefdom Created in the State | Production of all Maps of Chiefdom Created in the State | All LGAs | Bureau for Solid Minerals | Agency | Office of the Governor |  |  | Security, Peace and Unity |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-BPP-P-23-00001 | Renovation and Furnishing of BPP Office in Jalingo | Renovation and Furnishing of BPP Office in Jalingo | Jalingo | Bureau of Public Procurement (Due Process) | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 90000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-BPP-P-23-00002 | Construction of ICT Centre (Phase I) Jalingo | Construction of ICT Centre (Phase I) Jalingo | Jalingo | Bureau of Public Procurement (Due Process) | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 260000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-BPP-P-23-00003 | Provision of ICT Facility on the Existing Structure (Phase I) in Jalingo | Provision of ICT Facility on the Existing Structure (Phase I) in Jalingo | Jalingo | Bureau of Public Procurement (Due Process) | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-BPP-P-23-00004 | Sensitization/Seminar for Contractors & Suppliers e.t.c in Jalingo | Sensitization/Seminar for Contractors & Suppliers e.t.c in Jalingo | Jalingo | Bureau of Public Procurement (Due Process) | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-BSM-P-23-00001 | Exploration of Hydrocarborn Using Satllite on Benue Valley | Exploration of Hydrocarborn Using Satllite on Benue Valley | Jalingo | Bureau for Solid Minerals | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 80000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-BSM-P-23-00002 | Purchase of Equipment for Office Use | Purchase of Equipment for Office Use | Jalingo | Bureau for Solid Minerals | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Growing the Private Sector - General
SPDO-BSM-P-23-00003 | Renewal of all Mining Lease | Renewal of all Mining Lease | Jalingo | Bureau for Solid Minerals | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Growing the Private Sector - General
SPDO-BSM-P-23-00004 | Leasing of New Sites/Ocurrence | Leasing of New Sites/Ocurrence | Jalingo | Bureau for Solid Minerals | Agency | Office of the Governor |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Growing the Private Sector - General
SPDO-BTS-P-23-00001 | Payment of Domestic Scholarships | Payment of Domestic Scholarships | Jalingo | Taraba State Scholarship Board | Agency | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 380000000 |  | 0 | 0% |  |  | Inclusive Education
SPDO-BTS-P-23-00002 | Payment of Consolidated Scholarships | Payment of Consolidated Scholarships | Jalingo | Taraba State Scholarship Board | Agency | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Inclusive Education
SPDO-BTS-P-23-00003 | Payment of Scholarships for Physically Challenge Students | Payment of Scholarships for Physically Challenge Students | Jalingo | Taraba State Scholarship Board | Agency | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Inclusive Education
SPDO-BTS-P-23-00004 | Payment of Foreign Scholarships | Payment of Foreign Scholarships | Jalingo | Taraba State Scholarship Board | Agency | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Inclusive Education
SPDO-CCA-P-23-00002 | Renovation of Customary Court complex | Renovation of Customary Court complex | Jalingo | Customary Court of Appeal | Department | Ministry of Justice |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-COA-P-23-00001 | Construction of E - Library in the State | Construction of E - Library in the State | Jalingo | College of Agriculture, Jalingo | Department | Ministry of Agriculture and Food Security |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 33000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-COA-P-23-00006 | Rehabilitation & Construction of Feedmill Machinery | Rehabilitation & Construction of Feedmill Machinery | Jalingo | College of Agriculture, Jalingo | Department | Ministry of Agriculture and Food Security |  |  | Education |  | Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 16940000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-COA-P-23-00007 | Construction of Office/Hatchery Pen. | Construction of Office/Hatchery Pen. | Jalingo | College of Agriculture, Jalingo | Department | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Responsible Consumption & Production |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 21175000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-COA-P-23-00017 | Installation of 100 Numbers. of 20KVA Solar Panels | Installation of 100 Numbers. of 20KVA Solar Panels | Jalingo | College of Agriculture, Jalingo | Department | Ministry of Agriculture and Food Security |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 12000000 |  | 0 | 0% |  |  | Integrated rural development (agricultural land development, farm mechanization, & rural infrastructures
SPDO-COA-P-23-00018 | Renovation of Block of Storage of Feeds & Eggs | Renovation of Block of Storage of Feeds & Eggs | Jalingo | College of Agriculture, Jalingo | Department | Ministry of Agriculture and Food Security |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 826000 |  | 0 | 0% |  |  | Integrated rural development (agricultural land development, farm mechanization, & rural infrastructures
SPDO-COA-P-23-00019 | Renovation of Block of Entrepreuship Centre | Renovation of Block of Entrepreuship Centre | Jalingo | College of Agriculture, Jalingo | Department | Ministry of Agriculture and Food Security |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3066300 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-COE-P-23-00001 | Purchase of Fixed Assets and Materials for the College | Purchase of Fixed Assets and Materials for the College | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 800000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-COE-P-23-00002 | Construction/Provision of Fixed Assets (TETFund) | Construction/Provision of Fixed Assets (TETFund) | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 700000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-COE-P-23-00003 | Rehabilitation of Buidings and College Infrastructures | Rehabilitation of Buidings and College Infrastructures | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 550000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-COE-P-23-00004 | Convocation Programme in the College | Convocation Programme in the College | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Human and institutional capacity performance management
SPDO-COE-P-23-00005 | Accreditation of Courses at the College of Education, Zing | Accreditation of Courses at the College of Education, Zing | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Tertiary institutions’ new courses accreditation
SPDO-COE-P-23-00006 | Building of Staff Quarters | Building of Staff Quarters | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 450000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-COE-P-23-00007 | Completion of Abundant Projects at College of Education (COE), Zing | Completion of Abundant Projects at College of Education (COE), Zing | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 450000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-COE-P-23-00008 | Compensation of Land and Landed Properties | Compensation of Land and Landed Properties | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 683741653 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-COE-P-23-00009 | Puchase of Equipment at COE, Zing | Puchase of Equipment at COE, Zing | Zing | College of Education, Zing | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 830372232 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-COH-P-23-00001 | Construction of 2No. Six(6) Classroom | Construction of 2No. Six(6) Classroom | Takum | College of Health Technology, Takum | Department | Ministry of Health |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 130000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-COH-P-23-00002 | Construction of 10No. Room Examination and Record Complex | Construction of 10No. Room Examination and Record Complex | Takum | College of Health Technology, Takum | Department | Ministry of Health |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 111000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-COH-P-23-00003 | Construction of 1No. New Administration Block | Construction of 1No. New Administration Block | Takum | College of Health Technology, Takum | Department | Ministry of Health |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 374750246 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-COH-P-23-00004 | Construction of 15No. Staff Quarters | Construction of 15No. Staff Quarters | Takum | College of Health Technology, Takum | Department | Ministry of Health |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 209000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-CSA-P-23-00001 | Community and Social Development Agency Project Activities in the State (Rural infrastructure) | Community and Social Development Agency Project Activities in the State (Rural infrastructure) | All LGAs | Community & Social Development Agency | Agency | Ministry Finance Budget and Economic Planning |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-FCP-P-23-00001 | FADAMA CARES Project Activities/Purchase of Fixed Assets | FADAMA CARES Project Activities/Purchase of Fixed Assets | Jalingo | FADAMA CARES Project Support Unit | Department | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1588573000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-HCJ-P-23-00001 | Const. of High Court Judicial Division in Takum | Const. of High Court Judicial Division in Takum | Takum | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00002 | Construction of 15 Area Courts | Construction of 15 Area Courts | All LGAs | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00003 | Const.of High Court Judicial Division in Bali | Const.of High Court Judicial Division in Bali | Bali | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00004 | Construction of Magistrate Court Building in 5 LGAs Headquarters | Construction of Magistrate Court Building in 5 LGAs Headquarters | All LGAs | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00005 | Reconstruction of JSC Burnt Office Complex | Reconstruction of JSC Burnt Office Complex | Jalingo | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00006 | Construction of Judicial Division Karim | Construction of Judicial Division Karim | Karim Lamido | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00007 | Renovation of High Court Complex Gembu | Renovation of High Court Complex Gembu | Sardauna | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00008 | Purchase of Toyota LC 200 xv v8.8SLS Jeep for Hon. Chief Judge | Purchase of Toyota LC 200 xv v8.8SLS Jeep for Hon. Chief Judge | Jalingo | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 148000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00009 | Purchase of Toyota Land Cruiser Official Vehicles for 14 Judges | Purchase of Toyota Land Cruiser Official Vehicles for 14 Judges | Jalingo | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 310000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HCJ-P-23-00010 | Furnishing of Courts Newly constructed/Renovated Courts | Furnishing of Courts Newly constructed/Renovated Courts | Jalingo | High Court of Justice | Department | Ministry of Justice |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 400000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HSC-P-23-00001 | Renovation of Secretariate Complex & Extension | Rehabilitation/Remodeling of General Sani Abacha State Secretariat Complex, Jalingo | Jalingo | Office of the Head of Service (Career Management) | Office | Office of the Head of Service |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 1591632882.6 |  | 1591632882.6 | 50% |  |  | Reform of Government and Governance - General
SPDO-HSC-P-23-00002 | Construction of the Office of the Head of Service | Construction of the Office of the Head of Service | Jalingo | Office of the Head of Service (Career Management) | Office | Office of the Head of Service |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HSC-P-23-00003 | Contruction of State & Local Auditor General | Contruction of State & Local Auditor General | Jalingo | Office of the Head of Service (Career Management) | Office | Office of the Head of Service |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HSC-P-23-00004 | Contruction of Minisrty of Justice Office | Contruction of Minisrty of Justice Office | Jalingo | Office of the Head of Service (Career Management) | Office | Office of the Head of Service |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HSD-P-23-00008 | Purchase and Stocking of Books in the Resource center | Purchase and Stocking of Books in the Resource center | Jalingo | Office of the Head of Service (Manpower Development) | Office | Office of the Head of Service |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HSD-P-23-00009 | Provision for Research and Development | Provision for Research and Development | Jalingo | Office of the Head of Service (Manpower Development) | Office | Office of the Head of Service |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-HSD-P-23-00010 | ASCON State Government Officers Engagement | ASCON State Government Officers Engagement | Jalingo | Office of the Head of Service (Manpower Development) | Office | Office of the Head of Service |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-IVP-P-23-00001 | Agricultural Market Development | Agricultural Market Development | Jalingo | IFAD - VCD Project Support Unit | Department | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 915237404.5 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-IVP-P-23-00002 | Smallholder Productivity Enhancement | Smallholder Productivity Enhancement | Jalingo | IFAD - VCD Project Support Unit | Department | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 563032070 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-IVP-P-23-00003 | Coordination of International Fund for Agricultural Development Programme in the State | Coordination of International Fund for Agricultural Development Programme in the State | Jalingo | IFAD - VCD Project Support Unit | Department | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 168800000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-LSC-P-23-00001 | Local Government Staff Training Fund | Local Government Staff Training Fund | Jalingo | Local Government Service Commission (LGSC) | Agency | Ministry of Education |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 185000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MAG-P-23-00001 | Renting of Office and House for Integrated Farm ltd | Provision of office/house accommodation for staff of Gassol Integrated Farms ltd | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/01/2024 | 4 | Completed | 30000000 |  | 30000000 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00002 | Techno Feasibility Studies for the Development of special Agro-Industrial Processing Zone | Establishment of industrial hubs in the three senatorial zones of the state | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-02 | 31/05/2024 | 16 | Completed | NA |  | 305924000 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00003 | Soya Beans Production Programme | Soya Beans Production Programme (C-19) | All LGAs; | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-01-25 | 2023-09-28 | 39 | Completed | 50000000 |  | 50000000 | 100% | Yes | Boost Internally Generated Revenue through empowerment | Climate Change | No
SPDO-MAG-P-23-00004 | Procurement of 100,000 MT of assorted fertilizers | To Increase crop yield and ensure food security | All LGAs | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-05-30 | 30/06/2026 | 216 | Completed | 6714000000 |  | 6655036585.37 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00005 | Renovation of Green House Project | Provision of all year round quality vegetables for both local and international consumption  Creation of job opportunities for our teeming youths.  Technology transfer | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-01 | 30/07/2026 | 28 | Completed | 1795218118 |  | 1942895367 | 108.2% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00006 | Purchase of 10,000 MT assorted Grains under the Buffer stock programme | Reduction of hunger for the vulnerable populace | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-01 | 30/07/2026 | 28 | Completed | 1324368488.6 |  | 992212737.48 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00007 | Payment for State Insurance Premium Contribution | To mitigate against various risk associated with agricultural production | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-01 | 31/12/2025 | 54 | Completed | 57830640 |  | 57830640 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00016 | Renovation of Green House Project | Renovation and expansion | Jalingo; | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-01-25 | 2023-07-02 | 28 | Ongoing | 500000000 |  | 2252895367 | 145% | Yes | IGR through sales of vegetables | Legal, policy, regulations and standards, guidelines and protocols development and reviews | No
SPDO-MAG-P-23-00008 | Taraba Accelerated Agricultural and Rural Development Scheme (TAARDS) Phase 1 |  To improve the income and livelihood of farmers and rural households  Massive food production  To provide rural infrastructures such as roads, irrigation storage facilities and market.  To improve farmers’ access to quality input, credit extension services and modern farming technology.  To promote employment opportunities and reduce poverty in rural communities  To encourage value addition | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-01 | 30/07/2026 | 28 | Ongoing | 37250000000 |  | 9403839000 | 25.25% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00009 | Construction of Special Agro Processing Zones (SAPZII) in Lau, K-Lamido and Wukari LGAs | To enhance value addition of agricultural produce.  Maximize food preservation and increase shelf life of agricultural produce | Lau, Karim, Wukari | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-03 | 30/06/2025 | 12 | Ongoing | 690000000 |  | 313574000 | 45.45% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00010 | Training on Seed Multiplication in India | To equip Youth on modern seed multiplication techniques | Others (Outside the state); | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-01 | 30/06/2026 | 24 | Completed | 400000000 |  | 351183200 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00011 | Purchase of Certified Assorted Seeds for Agricultural Development in the State. | To increase crop yield and enhance food security in the state | All LGAs | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-05-30 | 30/06/2026 | 216 | Completed | 3575239199.6 |  | 2733060000 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00012 | Purchase of 500,000 Bundles of TME419 Cassava Stems for Distribution to Farmers in the State | To enhance availability of highly productive and improved cassava stems to farmers in the state. | All LGAs | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-05-30 | 30/06/2025 | 212 | Completed | 640000000 |  | 640000000 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00013 | Procurement of Agro Chemicals (Herbicides) and Equipment (Knapsack Sprayers) in Taraba State | To enhance crop protection and boost crop yield | All LGAs | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-05-30 | 30/06/2026 | 216 | Completed | 3055798500 |  | 1334900000 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00014 | Procurement Of 18No. Mini Storage Bins 10mt Capacity in Jalingo | To enhance storage of agricultural produce | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-05-30 | 30/06/2026 | 216 | Completed | 856970165.32 |  | 40000000 | 100% | No |  | Economic Empowerment | No
SPDO-MAG-P-23-00015 | Agro Data Collection for Agricultural Research and Development in the State | Agro Data Collection for Agricultural Research and Development in the State | All LGAs; | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-02 | 2024-07-13 | 14 | Not Started | 30613923.53 |  | 0 | 0% | No |  | Agricultural data and statistic management and institutionalisation of information and communication technology (ICT) | No
SPDO-MAG-P-23-00022 | Purchase of Fishing gears and accessories | Fish processing and post-harvest management | All LGAs; | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | No Poverty |  | 2024-01-25 | 2024-09-28 | 36 | Not Started | 50000000 |  | 0 | 0% | No |  | Commercial aquaculture development (fish production, feed mills development, fishing inputs etc.) | No
SPDO-MAG-P-23-00023 | Campaign against Obnoxious fishing | Sensitization against bad fishing method | All LGAs; | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-14 | 2024-07-10 | 25 | Not Started | 30633400.36 |  | 0 | 0% | Yes | Fish processing and post-harvest management | Economic Empowerment | No
SPDO-MAG-P-23-00029 | Procurement of Tractors and power Tiller | Procurement of 850Unit of Cabrio Compact Tractors Power Tiller. | Jalingo; | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-01-25 | 2023-09-28 | 33 | Ongoing | 300000000 |  | 81000000 | 27% | No |  | COVID-19 | No
SPDO-MAG-P-23-00035 | Purchase of Grains under the Buffer Stock of Agricultural Programme | Purchase of Grains under the Buffer Stock of Agricultural Programme | All LGAs; | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-07-01 | 2023-12-09 | 26 | Ongoing | 71754525.6 |  | 64095000 | 89% | No |  | COVID-19 | No
SPDO-MAG-P-23-00038 | Purchase of Certified Assorted Seeds for Agricultural Development | Purchase of Certified Assorted Seeds for Agricultural Development | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/12/2024 | 52 | Ongoing | 975239999.6 | 975239999.6 | 2541100000 | 260.6% | No |  | Crop value chains and food systems promotion (food and cash crops of state’s comparative advantage)
SPDO-MAG-P-23-00039 | Provision for National Agricultural Programme at Abuja FCT. | Provision for National Agricultural Programme at Abuja FCT. | Abuja | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-02 | 31/12/2025 | 52 | Ongoing | 35000000 | 35000000 | 15000000 | 42.86% | No |  | Public Private Partnerships (corporate private sector, NGOs, donors & development partners, farmers organizations)
SPDO-MAG-P-23-00040 | Provision and Plantation of Cassava in the State | Provision and Plantation of Cassava in the State | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-03 | 31/12/2026 | 52 | Ongoing | 270000000 | 270000000 | 80000000 | 30% | No |  | Crop value chains and food systems promotion (food and cash crops of state’s comparative advantage)
SPDO-MAG-P-23-00041 | Procurement of NPK and Urea Fertilizers to Farmers for Improved Seeds in the State | Procurement of NPK and Urea Fertilizers to Farmers for Improved Seeds in the State | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-04 | 31/12/2027 | 52 | Ongoing | 500000000 |  | 664536585.37 | 133% | No |  | COVID-19 - General
SPDO-MAG-P-23-00042 | Purchase of Agro Chemicals and Equipment in the Taraba State | Purchase of Agro Chemicals and Equipment in the Taraba State | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | End Poverty in all its forms |  | 2024-01-05 | 31/12/2028 | 52 | Not Started | 300798500 |  | 0 | 0% | No |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-MAG-P-23-00043 | Completion of Jalingo Modern Abattoir | Meat Inspection and Hygiene | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-06 | 31/12/2024 | 52 | Ongoing | 2000000000 | 800000000 | 2134130341.46 | 267% |  |  | Meat processing and marketing
SPDO-MAG-P-23-00044 | Procurement and Distribution of Agricultural Lime | Procurement and Distribution of Agricultural Lime | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | End Poverty in all its forms |  | 2024-01-07 | 31/12/2030 | 52 | Not Started | 360000000 |  | 0 | 0% |  |  | Integrated rural development (agricultural land development, farm mechanization, & rural infrastructures
SPDO-MAG-P-23-00046 | Procurement of Tractors and Implements/Accessories | Procurement of Tractors and Implements/Accessories | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Responsible Consumption & Production |  | 2024-01-08 | 2031-12-31 | 52 | Completed | 14823031560 |  | 1184561010.39 | 100% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MAG-P-23-00047 | Purchase of Heavy Duty Equipment | Purchase of Heavy Duty Equipment | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-09 | 31/12/2032 | 52 | Not Started | 18714938.82 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MAG-P-23-00048 | Cadre Harmonized (CH) Survey, data analysis and consollidation | Cadre Harmonized (CH) Survey, data analysis and consollidation | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-10 | 31/12/2033 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Agricultural data and statistic management and institutionalisation of information and communication technology (ICT)
SPDO-MAG-P-23-00049 | Purchase of fishing Equipment and Stocking of Fish at Tunga Dam (Sardauna) | Purchase of fishing Equipment and Stocking of Fish at Tunga Dam (Sardauna) | Sardauna | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Zero Hunger |  | 2024-01-11 | 31/12/2034 | 52 | Not Started | 55000000 |  | 0 | 0% |  |  | Commercial aquaculture development (fish production, feed mills development, fishing inputs etc.)
SPDO-MAG-P-23-00050 | Livestock Supplementary Feed Programme | Livestock Supplementary Feed Programme | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Zero Hunger |  | 2024-01-12 | 31/12/2035 | 52 | Not Started | 288334455 |  | 0 | 0% |  |  | Livestock feeds development
SPDO-MAG-P-23-00051 | Livestock Productivity & Resilience Support Project (L - PRES) Counterpart Fund | Livestock Productivity & Resilience Support Project (L - PRES) Counterpart Fund | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Zero Hunger |  | 2024-01-13 | 31/12/2036 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Livestock feeds development
SPDO-MAG-P-23-00052 | Provision of Veterinary Drugs & Vaccines for Disease Control | Provision of Veterinary Drugs & Vaccines for Disease Control | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-14 | 31/12/2037 | 52 | Ongoing | 70578080.5 |  | 37000000 | 52% |  |  | Integrated rural development (agricultural land development, farm mechanization, & rural infrastructures
SPDO-MAG-P-23-00053 | Purchase of fishing Equipment and Stocking of Fish at Kashimbila Dam (Takum) | Purchase of fishing Equipment and Stocking of Fish at Kashimbila Dam (Takum) | Takum | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | End Poverty in all its forms |  | 2024-01-15 | 31/12/2038 | 52 | Not Started | 55000000 |  | 0 | 0% |  |  | Commercial aquaculture development (fish production, feed mills development, fishing inputs etc.)
SPDO-MAG-P-23-00054 | Procurement of 26No. MotorCycles and 5No. Flying Boats | Procurement of 26No. MotorCycles and 5No. Flying Boats | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | End Poverty in all its forms |  | 2024-01-16 | 31/12/2039 | 52 | Not Started | 65900000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MAG-P-23-00055 | Construction and Maintainance of 1No. Solar Vaccines Cold | Construction and Maintainance of 1No. Solar Vaccines Cold | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-17 | 31/12/2040 | 52 | Not Started | 11445000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MAG-P-23-00056 | Procurement of Mini Storage Bins 10mt capacity | Procurement of Mini Storage Bins 10mt capacity | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | End Poverty in all its forms |  | 2024-01-18 | 31/12/2041 | 52 | Not Started | 25304620.32 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MAG-P-23-00057 | Management of Nappier Grass Farm at Mayo Kam Ranch Site | Management of Nappier Grass Farm at Mayo Kam Ranch Site | Bali | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-19 | 31/12/2042 | 52 | Not Started | 11665545 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MAG-P-23-00058 | Provision of Food and Nutrition Activities in the State | Provision of Food and Nutrition Activities in the State | Jalingo | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-01-20 | 31/12/2043 | 52 | Not Started | 41797139.31 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MAG-P-23-00059 | Esstablishment of Aquaculture and Fingerling production in 3 Geopolitical Zones | Esstablishment of Aquaculture and Fingerling production in 3 Geopolitical Zones | All LGAs | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-01-21 | 31/12/2044 | 52 | Not Started | 436000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MAG-P-23-00060 | Development of Marmi Fish Pond | Development of Marmi Fish Pond | Bali | Ministry of Agriculture & Food Security | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-22 | 31/12/2045 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MCP-P-23-00001 | Monitoring of skills Acquisition Centres | To Access the number and state of the Centres in the State | All LGAs | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-02 | 14/02/2024 | 4 | Completed | 2500000 |  | 2500000 | 100% |  |  | Poverty Alleviation - General
SPDO-MCP-P-23-00002 | Construction of Warehouse | Construction of warehouses at the three senatorial zones | Wukari, Bali and Zing | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2023-10-18 | 2023-12-31 | 52 | Not started | 600000000 |  | 0 | 0% |  |  | Poverty Alleviation - General
SPDO-MCP-P-23-00003 | TR-CARES Special Grant Transfer | To Cushion the Effects of COVID-19 Pandemic Amongs the Economically Active Youths and Women Between the Ages of 18-45 Cross the State | All LGAs | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2021-01-01 | 31/12/2024 |  | Ongoing | 150000000 |  | 150000000 | 100% |  |  | Poverty Alleviation - General
SPDO-MCP-P-23-00004 | Monitoring and Evaluation for Conditional Cash Transfer Activities | Conditional Cash Transfer M&E Support Activities | All LGAs; | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Decent Work and Economic Growth |  | 2023-12-01 | 2024-01-31 | 8 | Not Started | 136000000 |  | 0 | 0% | No |  | COVID-19 - General
SPDO-MCP-P-23-00005 | Educational Training for Cooperative Societies Across the 16 LGAs | Educational Training for Cooperative Societies Across The 16 LGA | All LGAs; | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Education |  | No Poverty |  | 2024-01-01 | 2024-02-29 | 8 | Not Started | 145192260 |  | 0 | 0% | No |  | Poverty Alleviation - General
SPDO-MCP-P-23-00006 | Baseline Survey (Cooperative Data Capture) | Baseline Survey (Cooperative Data Capture) | All LGAs; | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-02-29 | 8 | Not Started | 115000000 |  | 0 | 0% | No |  | Poverty Alleviation - General
SPDO-MCP-P-23-00007 | Procurement of Office Furniture | Procurement of Office Furniture | Jalingo; | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-03-30 | 12 | Not Started | 400000000 |  | 0 | 0% | No |  | Poverty Alleviation - General
SPDO-MCP-P-23-00008 | Trip to Abuja for Signing of MoU for the Transfer of Skills Acquisition Centre in Ibi From the Federal Ministry of Labour and Employment | To Formally Sign an MoU with the Ministry for Official Transfer of the Skills Acquisition Centre Built by The Federal Govenrment to the State | Others (Outside the state); | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-01-08 | 31/08/2023 | 52 | Completed | 5000000 |  | 5000000 | 100% |  |  | Poverty Alleviation - General
SPDO-MCP-P-23-00011 | Skills Acquisition Capacity Development Programme | Skills Acquisition Capacity Development Programme | Jalingo | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-01-26 | 31/12/2049 | 52 | Not Started | 800000000 | 0 | 0 | 0% | No |  | COVID-19 - General
SPDO-MCP-P-23-00012 | Workshop on Cooperative Matters (For Cooperative Society's Officials) | Workshop on Cooperative Matters (For Cooperative Society's Officials) | All LGAs | Ministry of Poverty Alleviation | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-01-27 | 31/12/2050 | 52 | Not Started | 25000000 | 0 | 0 | 0% | No |  | Poverty Alleviation - General
SPDO-MCT-P-23-00001 | Taraba woven Sack Factory(Phase I) | The project is a woven Sack Factory to be Located in Jalingo | Jalingo; | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2026-02-01 | 96 | Not Started | 40000000 |  | 0 | 0% | No | no | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00002 | Kefas Palliative Market, Jalingo | To boost the revenue of the State | Jalingo | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 24/10/2023 | 31/05/2024 | 48 | Completed | 3728437498.47 |  | 3728437498.47 | 100% | Yes | Market activities to generate revenue | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00003 | International Yam Market (Wukari) | International Yam Market (Wukari) | Wukari; | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-11-16 | 48 | ongoing | 9708475451.02 |  | 8299996716.995 | 45% | Yes | The project will generate IGR to Government through of revenue and taxes | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00004 | Organizing Taraba Investment Summit | Organizing the Taraba Economic Summit | Others (Outside the state); | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-04-11 | 1 | Not Started | 100000000 |  | 0 | 0% | No | Nil | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00005 | Establishment of Trade Facilitation Centre | Establishment of Trade Facilitation Center (one stop Investment Center) | Jalingo; | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-11-11 | 48 | Not Started | 50000000 |  | 0 | 0% | Yes | The project will bring in Investors into the state who are potential revenue payers | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00006 | Development of Industrial Layout @Tashan Nyamu | Development of Industrial layout | Ardo-kola; | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-11-11 | 48 | Not Started | 175000000 |  | 0 | 0% | Yes | Through payment of Taxes | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00007 | Construction of 2No. Area Commercial offices | Construction of three Area Commercial offices in Jalingo, Wukari and Bali | Bali;Jalingo;Wukari; | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-11-16 | 2024-11-11 | 48 | Not Started | 20000000 |  | 0 | 0% | Yes | The project will serve as Zonal revenue collection offices | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00008 | Provision for the Hosting of Trade Fair | Hosting of Tradefair | Others (Outside the state); | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-02-08 | 13 | Not Started | 20000000 |  | 0 | 0% | No | Nil | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00009 | Development of Website on Trade and investment | Development of website on trade and investment | Jalingo; | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-11-16 | 48 | Not Started | 200000000 |  | 0 | 0% | No | Nil | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00010 | Promotion of Export Activities in the State | Promotion of export activities | Jalingo; | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-11-16 | 48 | Not Started | 90000000 |  | 0 | 0% | No | Nil | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00011 | Purchase of 7No. Motorcycles | Purchase of 7No. Motorcycles | Jalingo | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-11-16 | 2024-11-16 | 48 | Not Started | 20000000 |  | 0 | 0% | No | Nil | Reform of Government and Governance (General) | No
SPDO-MCT-P-23-00012 | Renovation and Upgrade of Trade Fair Complex, Jalingo | To foster trade relationship within and outside Nigeria | Jalingo | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-23 | 31/12/2046 | 52 | Ongoing | 8873927392.58 |  | 5500000000 | 40% |  |  | Reform of Government and Governance - General
SPDO-MCT-P-23-00013 | Establishment of Industrial Clusters for Fabrication & Welding | Establishment of Industrial Clusters for Fabrication & Welding | Jalingo | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-24 | 31/12/2047 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MCT-P-23-00014 | Contruction of Excibition Hall at Trade Fair Complex | Contruction of Excibition Hall at Trade Fair Complex | Jalingo | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-25 | 31/12/2048 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Ministry of Commerce, Trade & Industry
SPDO-MCT-P-23-00015 | Support & Enhancement of Commodity Association | Support & Enhancement of Commodity Association | All LGAs | Ministry of Commerce, Trade & Industry | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00001 | Contruction of Digital Hub and CBT Centre | Contruction of Digital Hub and CBT Centre | Jalingo; | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50518000 |  | 0 | 0% | Yes | Solutions produce to be sold out | Reform of Government and Governance - General | Yes | Upscaling of digital literacy
SPDO-MDI-P-23-00002 | Education Management System Data Collection/Smart Students | Biometric capturing of students and introduction of E-learning | All LGAs; | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-03 | 2024-09-27 | 36 | Not Started | 250000000 |  | 0 | 0% | No |  | Reform of Government and Governance - General | Yes | Educational Digitization
SPDO-MDI-P-23-00003 | Digital Literacy and Capacity building in (16 LGA) for Women and Youth | Capacity Building Program for Women and Youths | All LGAs; | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% | No |  | Reform of Government and Governance - General | Yes | Digital Literacy program
SPDO-MDI-P-23-00004 | Digital Solution for MDA/E-Commerce | Digital Solution for MDA/E-Commerce | All LGAs; | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-06-28 | 24 | Not Started | 80895670 |  | 0 | 0% | No |  | Reform of Government and Governance - General | No | Digital Literacy program
SPDO-MDI-P-23-00005 | State Digital Economy and Innovation (SDE&I) Policy and Strategy | State Digital Economy and Innovation (SDE&I) Policy and Strategy | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 45000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00006 | Procurement of 6 Digital Bill Boards for Advertisement | Procurement of 6 Digital Bill Boards for Advertisement | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-09-27 | 52 | Not Started | 50230500 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00007 | Procurement of Digital & ICT facilities for HUB and CBT | Procurement of Digital & ICT facilities for HUB and CBT | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00008 | Digital Biometric data Capturing for CSC | Digital Biometric data Capturing for CSC | All LGAs | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-06-28 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00009 | Establishment of SDITDA | Establishment of SDITDA | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-09-27 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00010 | Solar Electricity Installation | Solar Electricity Installation | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00011 | Contruction of Digital Hub in South/Central Zone of the State | Contruction of Digital Hub in South/Central Zone of the State | Wukari, Bali | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-06-28 | 52 | Not Started | 350000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00012 | Digitalization of Specialist Hospital | Digitalization of Specialist Hospital | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00013 | The Taraba State Digital transformation shop | Serve as one stop shop for every Data Centre for adoption of E-governance Pay station for provision of internet services for MDAs Monitor Traffic (CCTV) | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/03/2024 | 52 | Ongoing | 50000000 |  | 24200000 | 80% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00035 | Contribution to IGR Secure a deal with Computer Warehouse Group (CWG) in Collaboration with Ministries of Finance, Justice and Board of Internal Revenue | Less than 3m Focast 150m revenue Working with other Ministries and Agencies | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/03/2024 | 52 | Ongoing | 20000000 |  | 14000000 | 70% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00014 | Digital Base Station | Digital Processing Interfaces (DPI) to house the state’s digital solutions | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 30/6/2024 | 22 | Completed | 24600000 |  | 24600000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00015 | Digital Algorand Hackathon | To expose Taraba Youth to Tech skills locally | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-08 | 31/8/2024 | 4 | Completed | 42500000 |  | 42500000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00016 | Regional Hackathon | To expose Taraba Youth to Tech skills locally and Internationally | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-10 | 30/11/2024 | 8 | Completed | 248800000 |  | 248800000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00017 | Web3 Blockchain Training | To train youth on how to utilize Web3 technology to develop various aspects of the economy and solve numerous tech challenges. | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-08 | 31/8/2024 | 4 | Completed | 81200000 |  | 81200000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00018 | New Ministry’s Website | To improve effective communication and showcase the State potentials to the rest of the world | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-06 | 30/6/2024 | 4 | Completed | 3700000 |  | 3700000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00019 | Hosting of Build-A-Thon Holiday Booth Camp: | To equip teenagers with digital tech that will make them self-reliant | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-08 | 31/8/2024 | 4 | Completed | 36340000 |  | 36340000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00020 | Inclusion of 8 LGAs in Taraba State in the next phase of the Project 774 LG | To prepare Local Governments for E-Governance and improve inter connectivity between arms of Government within and outside the State | All LGAs | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-09 | 30/9/2024 | 4 | Completed | 19200000 |  | 19200000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00021 | National Enrollment | To enable the State get recognition as well as have a voice in national policies regarding Information Technology | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/1/2024 | 4 | Completed | 4250000 |  | 4250000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00022 | UNDP Project | To develop E- Learning and provide easy access to E- Learning facilities for students of tertiary Institution in the State | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-10 | 30/10/2024 | 4 | Completed | 19000000 |  | 19000000 | 100% |  |  | Reform of Government and Governance - General |  | Digital Literacy program
SPDO-MDI-P-23-00023 | National council on Digital Economy | Digital Competition to develop Youth in Digital solution the State | Others (Outside the state); | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-02 | 28/02/2024 | 4 | Completed | 4000000 |  | 4000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00024 | 1st Taraba State Digital Hackaton | Talents hunts in the areas of digital innovation and software developers among youth in the State | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-01-11 | 30/11/2023 | 4 | Completed | 5000000 |  | 5000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00025 | 1st Taraba State Digital Kids Bootcamp | Enhancing their skills in learning and research, communication skills and application of digital talents to solve societal problems | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-08 | 31/082024 | 4 | Completed | 20000000 |  | 20000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00026 | 2nd Taraba State Digital Hackaton | Talents hunts in the areas of digital innovation and software developers among youth in the State | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-12 | 31/12/2024 | 4 | Completed | 26000000 |  | 26000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00027 | 2nd Taraba State Digital Kids Bootcamp | Exposed teen ages to basic and intermediate digital competencies such as Computer Literacy, Internet Usage, Digital Entrepreneurship | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-08 | 31/08/2025 | 4 | Completed | 26000000 |  | 2600000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00028 | 3rd Taraba State Digital Hackaton | 200 youth Participants mostly in Digital Software Developers | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-11 | 30/11/2025 | 4 | Completed | 80000000 |  | 80000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00029 | 3rd Taraba State Digital Kids Bootcamp | Introduce Secondary school students to the digital world by teaching them Coding and Apps development | Wukari | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-04 | 30/04/2025 | 4 | Completed | 48000000 |  | 48000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00030 | Preparation to Canada for International Digital Expos | Preparation for Expo on digital innovation for 2 commissioners in | Others (Outside the state); | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-06 | 30/06/2025 | 4 | Completed | 25500000 |  | 25500000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00031 | International Digital Expos in Canada | the expo serves a gateway to global networking and connectivity in the digital innovation, education; advancement and career opportunities in the digital age | Others (Outside the state); | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-08 | 31/08/2025 | 4 | Completed | 98000000 |  | 98000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00032 | Digitalization/ Virtual Exco Meeting | E-government Implementation and Adoption | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-06 | 30/06/2026 | 4 | Completed | 90000000 |  | 90000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00033 | 4th Taraba State Digital Kids Bootcamp | Digital Literacy skills for teenage in primary and secondary schhols | Sardauna | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-08 | 30/09/2026 | 8 | Ongoing | 60000000 |  | 60000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MDI-P-23-00034 | 4th Taraba State Digital Hackaton | Connecting youth in Digital Software Innovators and Developers for further development | Jalingo | Ministry of Digital Economy & Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-08 | 30/09/2026 | 8 | Ongoing | 80000000 |  | 80000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MEC-P-23-00001 | Zoological Garden Renovation | Zoological Garden Renovation | Ardo-kola;Jalingo; | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-02 | 2024-12-10 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General | Yes | Recreation will attract participants that will be paying
SPDO-MEC-P-23-00002 | Rehabilitation of Divisional Forestry Offices | Rehabilitation of Divisional Forestry Offices | All LGAs; | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | No Poverty |  | 2024-04-03 | 2024-12-18 | 52 | Not Started | 246000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General | No
SPDO-MEC-P-23-00003 | Construction of 1No. Block of Climate Change Department Office | Construction of 1No. Block of Climate Change Department Office | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Security, Peace and Unity |  | Climate Action |  | 2023-11-29 | 2024-12-29 | 52 | Not started | 149500000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00004 | Renovation of Taraba Environmental Protection (TEPA) Office at Jalingo | Renovation of Taraba Environmental Protection (TEPA) Office at Jalingo | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2023-10-28 | 2024-11-26 | 52 | Not started | 30000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00005 | Const. & Equiping of Environmental Reference Lab. | Const. & Equiping of Environmental Reference Lab. | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00006 | Subvention to Ngel Nyaki Mountain Resort | Subvention to Ngel Nyaki Mountain Resort | Sardauna | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 40000000 |  | 20000000 | 50% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00007 | Control & Management of Marauding Animals | Control & Management of Marauding Animals | Gashaka | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00008 | Aforestation & Re - Aforestation Scheme/Jathropha Plantation | Aforestation & Re - Aforestation Scheme/Jathropha Plantation | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 30/09/2024 | 52 | Ongoing | 3100000000 |  | 384900000 | 12% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00009 | Forest & Game Reserve Monitoring/Promotion | Forest & Game Reserve Monitoring/Promotion | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 28000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00010 | Conduct of Soil Survey for Baseline Data/Solution in Jalingo, Yorro, Sardauna, Bali, Takum & Ibi LGAs | Conduct of Soil Survey for Baseline Data/Solution in Jalingo, Yorro, Sardauna, Bali, Takum & Ibi LGAs | Jalingo, Yorro, Sardauna, Bali, Takum, Ibi | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00011 | Provision for the Planting of Grasses, Omamental Plants & Flowers in Jalingo | Provision for the Planting of Grasses, Omamental Plants & Flowers in Jalingo | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3200000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00012 | Establishment of Environmental Clubs in GSS Zing, GDSS M/Biyu and GSSS Donga | Establishment of Environmental Clubs in GSS Zing, GDSS M/Biyu and GSSS Donga | Zing, Gassol, Donga | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00013 | Establishment of Weather Station in Jalingo, Bali & Wukari | Establishment of Weather Station in Jalingo, Bali & Wukari | Jalingo, Bali, Wukari | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00014 | Const. & Equiping of Environmental Reference Library | Const. & Equiping of Environmental Reference Library | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 160000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00015 | Purchase of Chemicals for Cleaning and Fumigation in Jalingo, Wuk and Bali | Purchase of Chemicals for Cleaning and Fumigation in Jalingo, Wuk and Bali | Jalingo, Wukari, Bali | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00016 | Conduct of Environmental Impact Assessment Procedure & Guideline | Conduct of Environmental Impact Assessment Procedure & Guideline | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00017 | Standardization of Solid Waste Management Protection Development | Standardization of Solid Waste Management Protection Development | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00018 | Provision for Raising of Seedlings to Control Climate Change and Erosion | Provision for Raising of Seedlings to Control Climate Change and Erosion | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2500000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00019 | Establishment & Equipping of a Gas Emission Control Centre in Jalingo | Establishment & Equipping of a Gas Emission Control Centre in Jalingo | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 8000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00020 | Procurement of 3000No. Cooking Stoves & 6kg Cylinder for Climate Change Mitigation | Procurement of 3000No. Cooking Stoves & 6kg Cylinder for Climate Change Mitigation | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 249784041.28 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00021 | Rehabilitation of Nursery & Forest Plantation | Rehabilitation of Nursery & Forest Plantation | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1690500000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00022 | Establishment of Urban Garden in Jalingo, Zing, Bali & Wukari | Establishment of Urban Garden in Jalingo, Zing, Bali & Wukari | Jalingo, Zing, Bali, Wukari | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00023 | Climate Change Mitigation | Climate Change Mitigation | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1100000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00024 | Resurvey and Beaconing of Baissa, Abong and Bantaje Forest Reserve | Resurvey and Beaconing of Baissa, Abong and Bantaje Forest Reserve | Kurmi, Wukari | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4330000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00025 | Provision for 7No. ICT Equipment | To provide computers to staff for office use | Jalingo | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2025-01-01 | 2025-12-31 | 52 | Completed | 10000000 |  | 11000000 | 100% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00026 | Provision for Mitigation of Deforestation Activities in the State | Provision for Mitigation of Deforestation Activities in the State | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00027 | Coordination of Green Wall Project activities in the State | Coordination of Green Wall Project activities in the State | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEC-P-23-00028 | Coordination of ACReSAL Project activites in the State | Coordination of ACReSAL Project activites in the State | All LGAs | Ministry of Environmental and Climate Change | Ministry | Ministry |  |  | Economic and Job Creation |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MED-P-23-00001 | Construction, Renovation And Remodelling Of Government Day Secondary School Nyamusala, Jalingo | Renovation Of 5 Blocks Of 3 Classrooms And Construction Of 2 Set Upstairs | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 44935 | 31/03/2024 | 24 | Completed | 631219465.87 |  | 631219465.87 | 100 |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00002 | Renovation of temporary site of Government Comprehensive Secondary School ( Student Exchange) at Federal Science and Technical College, Jalingo (FSTC) | Renovation of some facilities such as Students and Staff Furnitures, Students Accommodation, Replacement of doors, windows and toilet facilities. | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 44934 | 30/09/2023 | 8 | Completed | 48000000 |  | 48000000 | 100 |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00003 | State Contribution for Development Partners | State Contribution for Development Partners | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-10-01 | 2023-12-31 | 12 | Ongoing | 150000000 |  | 100000000 | 66.67% |  |  | Integrated supportive supervision
SPDO-MED-P-23-00004 | Payment of WAEC and NECO Examination Fees for JSS 3 and SSS 3 Students in the State | To relief parents the burden of the cost of their wards external examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-01-12 | 30/06/2023 | 28 | Completed | 1344136088 |  | 1344136088 | 100% |  |  | School examination and MLA
SPDO-MED-P-23-00005 | Perimeter Fencing in 30No. Secondary Schools in the 3-Senatorial District in the State | Perimeter Fencing in 30No. Secondary Schools in the 3-Senatorial District in the State | Zones | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-10-01 | 2023-12-31 | 12 | Ongoing | 500873808 |  | 30285000 | 6.05% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00006 | Remodelling of Ebenezer Primary School, Wukari | Remodeling of Ebenezer primary school, Wukari | Wukari | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-10-01 | 2023-12-31 | 12 | Not Started | 148537262 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00007 | Renovation of TASU hostel | To afford the institution with accommodation for Students | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 500000000 |  | 500000000 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00008 | Accreditation of courses in TSU | To afford the institution with courses recognized by NUC | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 700000000 |  | 700000000 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00009 | International travel | Educational Study tour to Finland | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-02-10 | 30/10/2023 | 4 | Completed | 164053437.55 |  | 164053437.55 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00010 | International travel | Educational Study tour to Finland | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-02 | 28/02/2024 | 4 | Completed | 156698750 |  | 156698750 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00011 | Construction of students benches and desks for some Secondary Schools in the State Headquarters | To provide sitting accommodation for students to comfortably write their sterna exams | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 30/04/2024 | 16 | Completed | 200500000 |  | 32000000 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00012 | Production of Scheme of work for secondary schools in the State | To ensure that there is uniformity in the teaching content across the secondary schools in the State | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 30/04/2024 | 16 | Completed | 26309200 |  | 26309200 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00013 | Procurement of Hydro foam bricks technology for construction of Schools infrastructure | To afford the State Technical Collages the Machines for Block Molding skills | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-03 | 31/12/2024 | 40 | Completed | 5666019340 |  | 5286694340 | 100% |  |  | ICT equipment, software and expertise
SPDO-MED-P-23-00014 | Procurement of uniforms and Instructional Materials | To reduce financial burden on parents and enhance teaching and learning in schools | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/12/2024 | 54 | Ongoing | 58656038740 |  | 10000000000 | 17% |  |  | Inclusive Education
SPDO-MED-P-23-00015 | Constructing of Parameter Fence of Government Secondary School, Wukari | Constructing of Parameter Fence of Government Secondary School, Wukari | Wukari | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-10-01 | 2023-12-31 | 12 | Not Started | 500000000 |  | 0 | 0%
SPDO-MED-P-23-00016 | Travel for a Joint Consultative Committee on Education in Calaber | To expose director of the ministry on the rudiment of Educational policy formulation | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-05 | 31/05/2024 | 4 | Ongoing | 97045308.01 |  | 3630000 | 3.7% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00017 | Procurement of Instructural Materials | Procurement of equipment & instructional materials for all primary and secondary Schools. | Sardauna, Bali, Jalingo, Takum, K/Lamido, Wukari and Zing | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-10-01 | 2023-12-31 | 12 | Ongoing | 196743000 |  | 58309200 | 30% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MED-P-23-00018 | Construction of 7No. Workshop Centres in 7No. Technical Schools (Zing, K/Lamido, Sardauna, Takum, Wukari, Jalingo & Bali LGAs) | Equipping 7No. Technical/Vocational Schools (Gembu, Bali, Jalingo, Takum, K/Lamido, Wukari and Zing) | Zing, Bali, Karim Lamido, Sardauna, Wukari, Jalingo, Takum | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 45200 | 45291 | 12 | Not Started | 448206104 |  | 0 | 0 |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00019 | Travel for workshop on practical Intelligence in Abuja | Capacity Building | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-04 | 30/04/2024 | 4 | Ongoing | 93415308.01 |  | 2000000 | 2.1% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00020 | Travel for World Bank Assisted project on Human Capital Opportunity | Capacity Building | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-05 | 20/05/2024 | 4 | Ongoing | 93005308.01 |  | 410000 | 0.44% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00021 | Conduct of Computer Based quiz and football competition among Primary & Secondary Schools Student in southern Taraba | To discover skilled and talented students | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-04 | 30/04/2024 | 4 | Ongoing | 13224700 |  | 10000000 | 75% |  |  | ICT equipment, software and expertise
SPDO-MED-P-23-00022 | Sponsoring students of FGGC for international competition to Rwanda | To showcase some of the best minds at international level | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-04 | 30/04/2024 | 4 | Ongoing | 92340000 |  | 10000000 | 10.9% |  |  | Inclusive Education
SPDO-MED-P-23-00023 | Attending Stakeholders Validation meeting on draft National Minimum Standard in Abuja | To represent the State and make her input in the document | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-04 | 30/04/2024 | 4 | Ongoing | 97045308.01 |  | 1000000 | 1.03% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00024 | Honorable Commissioner’s medical Bill | Treatment for the Honorable Commissioner | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-03 | 31/03/2024 | 4 | Ongoing | 41782150 |  | 12389430 | 29.7% |  |  | Health
SPDO-MED-P-23-00025 | Procurement of Sporting/Games Facilities for Schools | Procurement of Sporting/Games Facilities for Schools | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-02 | 2025-01-01 | 52 | Not Started | 98200000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00026 | Procurement and Maintenance of EMIS ICT Facilities in the Ministry & 30No. Secondary Schools | Procurement and Maintenance of EMIS ICT Facilities in the Ministry & 30No. Secondary Schools | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-03 | 2025-01-02 | 52 | Not Started | 130891000 |  | 0 | 0% |  |  | ICT equipment, software and expertise
SPDO-MED-P-23-00027 | Provision for Student's Exchange Programme in the State | Provision for Student's Exchange Programme in the State | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/07/2024 | 28 | Ongoing | 175912000 |  | 225144620 | 122% |  |  | Inclusive Education
SPDO-MED-P-23-00028 | Renovation of 2No. Unity Schools (MGGS Wukari & GCSS Jalingo) | Renovation of 2No. Unity Schools (MGGS Wukari & GCSS Jalingo) | Jalingo, Wukari | Ministry of Education | Ministry | Ministry |  |  | Education |  | Education |  | 2024-01-05 | 2025-01-04 | 52 | Ongoing | 202000000 |  | 13514700 | 6.6% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00029 | Renovation of 2No. Blocks of 3No. Class Rooms in 30No. Secondary Schools | Renovation of 2No. Blocks of 3No. Class Rooms in 30No. Secondary Schools | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Education |  | 2024-01-06 | 2025-01-05 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00030 | Construction of ERC Office | Construction of ERC Office | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-07 | 2025-01-06 | 52 | Not Started | 240601772 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00031 | Procurement of ICT Facilities for ERC | Procurement of ICT Facilities for ERC | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-08 | 2025-01-07 | 52 | Not Started | 150503000 |  | 10848890.6 | 7% |  |  | ICT equipment, software and expertise
SPDO-MED-P-23-00032 | Teaching and non-teaching staff capacity building | Teaching and non-teaching staff capacity building | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-09 | 2025-01-08 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Teaching and non-teaching staff capacity building
SPDO-MED-P-23-00033 | Conduct of Annual School Census/Schools Record Training | Conduct of Annual School Census/Schools Record Training | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-10 | 2025-01-09 | 52 | Not Started | 81129798 |  | 0 | 0% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00034 | Purchase of Science Chemicals & Laboratory Equipment in Schools | Purchase of Science Chemicals & Laboratory Equipment in Schools | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-11 | 2025-01-10 | 52 | Ongoing | 300586524.72 |  | 40000000 | 13.31% |  |  | Instructional and learning materials
SPDO-MED-P-23-00035 | Construction of State Library Complex in Jalingo | Construction of State Library Complex in Jalingo | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-12 | 2025-01-11 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00036 | Coordination of IDPs Pupils/Students in the State | Coordination of IDPs Pupils/Students in the State | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Security, Peace and Unity |  | End Poverty in all its forms |  | 2024-01-13 | 2025-01-12 | 52 | Not Started | 105230000 |  | 0 | 0% |  |  | Integrated supportive supervision
SPDO-MED-P-23-00037 | Provision for National and State Sport Festival at Jalingo, Abuja FCT | Provision for National and State Sport Festival at Jalingo, Abuja FCT | Jalingo, Abuja | Ministry of Education | Ministry | Ministry |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-14 | 2025-01-13 | 52 | Ongoing | 215000000 |  | 10000000 | 4.6% |  |  | Advocacy and sensitization
SPDO-MED-P-23-00038 | Construction of 6No. Model Secondary School in Jalingo | Construction of 6No. Model Secondary School in Jalingo | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-15 | 2025-01-14 | 52 | Not Started | 3118642958.72 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00039 | Creation of Ministry Website and e-Learning Portal | Creation of Ministry Website and e-Learning Portal | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-16 | 2025-01-15 | 52 | Not Started | 245349000 |  | 0 | 0% |  |  | ICT equipment, software and expertise
SPDO-MED-P-23-00040 | Procurement of Workshop Equipment for 7No. Technical Schools | Procurement of Workshop Equipment for 7No. Technical Schools | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-17 | 2025-01-16 | 52 | Not Started | 5286694340 |  | 5286694340 | 100% |  |  | Teaching and non-teaching staff capacity building
SPDO-MED-P-23-00041 | Conduct of BECE and Mock Examination (Production, Monitoring & Marking) | To relief parents the burden of the cost of their wards internal examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-01-12 | 31/10/2024 | 32 | Completed | 234000000 |  | 234000000 | 100% |  |  | School examination and MLA
SPDO-MED-P-23-00042 | Provision for National and State Quiz Competition | Provision for National and State Quiz Competition | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-19 | 2024-04-18 | 52 | Ongoing | 13224700 |  | 8196610 | 61.9% |  |  | School examination and MLA
SPDO-MED-P-23-00043 | School Farm and Garden (Primary and Secondary) | School Farm and Garden (Primary and Secondary) | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Zero Hunger |  | 2024-01-20 | 2025-01-19 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MED-P-23-00044 | Procurement of Teachers and Students Textbooks (Primary & Secomdary) | Procurement of Teachers and Students Textbooks (Primary & Secomdary) | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-21 | 30/10/2025 | 52 | Ongoing | 3915580800 |  | 1500000000 | 38% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00045 | Other maintenance services for schools | To provide running Cost for the up-keep of primary and secondary schools in the State | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-01-09 | 31/12/2024 | 60 | Ongoing | 883548000 |  | 542109500 | 61% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00046 | Accreditation of courses in COE | To afford the institution with courses recognized by NCCE | Zing | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 230000000 |  | 230000000 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00047 | Parameter fencing of GDSS Sabon-Gari | To provide security and control entrustment into the school | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/12/2024 | 52 | Ongoing | 500873808.52 |  | 36285000 | 7% |  |  | School Infrastructure Construction and Rehabilitation
SPDO-MED-P-23-00048 | National youth service corps (NYSC) | To motivate corps members teaching in Secondary Schools across the State. | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Peace, Justice and Strong Institutions |  | 2024-01-07 | 30/09/2024 | 12 | Completed | 152775500 |  | 152775500 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00049 | Placement of JSS 1 Students. Nigerian Military School Examination in to JSS 1 | To afford Taraba indigene gain placement into Junior Secondary schools | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/07/2024 | 28 | Ongoing | 50218000 |  | 48575500 | 96.7% |  |  | School Examination and MLA
SPDO-MED-P-23-00050 | International Trip | To explore and buy into educational innovation for the State | Others (Outside the state); | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/12/2024 | 52 | Ongoing | 376290000 |  | 282376234.52 | 75% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00051 | College of Education, Zing Convocation/Graduation Ceremony. | To Certificate graduands of the College and to meet up with the NCCE Guidelines. | Zing | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-10 | 31/10/2024 | 4 | Completed | 199880000 |  | 199880000 | 100% |  |  | Institutional and Learning Materials
SPDO-MED-P-23-00052 | Meeting of His Excellency's the Executive Governor with Head teachers/ Principals of Public Schools. | To Evaluate the progress of free and Compulsory Education Policy in the State. | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-10 | 31/10/2024 | 4 | Completed | 180350000 |  | 180350000 | 100% |  |  | Advocacy and Sensitization
SPDO-MED-P-23-00053 | Lifting and feeding of Students Exchange program | Transportation and feeding of students exchange program | Jalingo | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/6/2025 | 24 | Ongoing | 228685600 |  | 219197785 | 95.85% |  |  | Inclusive Education
SPDO-MED-P-23-00054 | Registration and conduct of WAEC, NECO & NABTE 2025 | To relief parents the burden of the cost of their wards external examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/6/2025 | 24 | Completed | 1631230000 |  | 1153343040 | 100% |  |  | School examination and MLA
SPDO-MED-P-23-00055 | Registration and conduct of BECE 2025 | To relief parents the burden of the cost of their wards internal examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/6/2025 | 24 | Ongoing | 200569655 |  | 125800353.35 | 72.72% |  |  | School examination and MLA
SPDO-MED-P-23-00056 | Procurement of Hydro foam bricks technology for construction of Schools infrastructure | For the construction of Modern primary and secondary schools across the State | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/6/2025 | 24 | Ongoing | 2450000000 |  | 1200000000 | 48.98% |  |  | ICT equipment, software and expertise
SPDO-MED-P-23-00057 | Construction of Model Primary and Secondary School in the 16 LGAs (60 schools) | To provide condusive learning environment | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/6/2025 | 24 | Ongoing | 34427369599.57 |  | 8100000000 | 23.53% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MED-P-23-00058 | Proactive prevention, control and extermination of termite anthills | To discover skilled and talented students | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/6/2025 | 24 | Completed | 50000000 |  | 50000000 | 100% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MED-P-23-00059 | Registration and conduct of NABTE, 2025 | To relief parents the burden of the cost of their wards external examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/10/2025 | 24 | Completed | 39011000 |  | 39011000 | 100% |  |  | School examination and MLA
SPDO-MED-P-23-00078 | Conduct of BECE Examination (Production, Monitoring & Marking) | To relief parents the burden of the cost of their wards internal examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-12 | 31/10/2025 | 32 | Completed | 200569655 |  | 170163353.35 | 100% |  |  | School examination and MLA
SPDO-MED-P-23-00060 | Conduct of Mock Examination (Production, Monitoring & Marking) | To relief parents the burden of the cost of their wards internal examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-12 | 31/10/2025 | 32 | Ongoing | 200569655 |  | 114385250 | 57.03% |  |  | School examination and MLA
SPDO-MED-P-23-00061 | Construction of students benches and desks for some Secondary Schools in the State Headquarters | To provide sitting accommodation for students to comfortably write their sterna exams | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/10/2025 | 16 | Ongoing | 235000000 |  | 46000000 | 19.57% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00062 | Project variation (prezzo shed invest limited, abuja). | Contract Review because of Increase in price of materials | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/10/2025 | 16 | Ongoing | 2450000000 |  | 700000000 | 28.57% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00063 | Procurement of 180 units of k-yan technology system for public primary and secondary schools in taraba state. | To improve effective Digital Teaching teaching and learning | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-01 | 30/10/2025 | 16 | Completed | 1904040000 |  | 1904040000 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00064 | Transportation Bill for Exchange Students | To Transport exchange students to various States | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-12 | 2026-02-03 | 12 | Ongoing | 300000000 |  | 52750490 | 17.58% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00065 | Feeding of two Unity Schools | To feed Students in two Unity Schools in the State | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-12 | 2026-02-03 | 12 | Ongoing | 300000000 |  | 148565040 | 49% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00066 | Registration and conduct of WAEC, 2026 | To relief parents the burden of the cost of Parents wards for external examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-12 | 2026-02-03 | 12 | Ongoing | 4340000000 |  | 10000000 | 0.2% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00067 | Payment of Salary | To relief parents the burden of the cost of their wards for external examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2025-01-12 | 2026-02-03 | 12 | Ongoing | 250000000 |  | 45270105.2 | 18.11% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00068 | Provision for Student's Exchange Programme in the State | To Transport exchange students to various States | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Ongoing | 300000000 |  | 286349700 | 95.45% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00069 | Registration and conduct of WAEC, NECO & NABTEB 2026 | To relief parents the burden of the cost of Parents wards for external examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Completed | 4340000000 |  | 3057720600 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00070 | Registration and conduct of BECE & MOCK | To relief parents the burden of the cost of their wards for external examinations | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Ongoing | 500000000 |  | 356681159.6 | 71.34% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00071 | Renovation of 2No. Unity Schools Marmara Government Girls Secondary School Wukari and Government College Secodary School Jalingo (MGGS Wukari & GCSS Jalingo) | To relief parents the burden of the cost of their wards for external examinations | Wukari | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Completed | 50000000 |  | 500000000 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00072 | Construction 60 Model Primary and Seondarys with hydrofoam bricks in Central, Northern and Southern Zones of the State | To provide safe learning environment for students & teachers | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Ongoing | 35000000000 |  | 10095960000 | 28.85% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00073 | Provision for National and State Quiz Competition in the State | To build the capacity of students for the national & state competition | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Completed | 120000000 |  | 113688750 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00074 | Procurement of Teachers and Students Textbooks (Primary & Secomdary) | To support effective teaching and learning | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Ongoing | 3915580800 |  | 3500000000 | 89.39% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00075 | Construction of School Fence and Security | To provide school safety and security | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-06-22 | 2026-07-22 | 4 | Ongoing | 692277368.02 |  | 692277368.02 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00076 | Salary | To pay the staff wages and salaries | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-01-01 | 2026-06-30 | 24 | Completed | 250000000 |  | 160234497.19 | 100% |  |  | Human and institutional capacity performance management
SPDO-MED-P-23-00077 | Distribution of School Uniform in the 16 LGAs | To support Free and Compulsory Education Agenda of His Excellency | All LGAs | Ministry of Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-01-01 | 2026-06-30 | 24 | Completed | 96600000 |  | 96600000 | 100% |  |  | Human and institutional capacity performance management
SPDO-MEE-P-23-00001 | Extension of 33kv From Line Suntai-Bali | Extension of 33kv From Line Suntai-Bali | Bali | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-22 | 2025-01-21 | 52 | Not Started | 1300000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00002 | Extension of 33kv line from lafia | Extension of 33kv line from lafia | All LGAs | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-24 | 2025-01-23 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00003 | Extension of 33kv Line From Wukari To Tsokundi With Township network | Extension of 33kv Line From Wukari To Tsokundi With Township network | Wukari | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-26 | 2025-01-25 | 52 | Ongoing | 250000000 |  | 1250000000 | 500% |  |  | Power - General
SPDO-MEE-P-23-00004 | Provision and maintenance of minigrid and Solar street light across the State | Provision and maintenance of minigrid and Solar street light across the State | All LGAs | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-27 | 2025-01-26 | 52 | Not Started | 550000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00005 | Connection of Ibbi/Wukari Water works to National Grid | Connection of Ibbi/Wukari Water works to National Grid | Ibbi, Wukari | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-28 | 2025-01-27 | 52 | Not Started | 80000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00006 | Provision for Solar Street Light in Jalingo | Provision for Solar Street Light in Jalingo | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-29 | 2025-01-28 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00007 | Rehabilitation/Upgrading of Rural Electrification and Minigrid of Gembu | Rehabilitation/Upgrading of Rural Electrification and Minigrid of Gembu | Sardauna | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-30 | 2025-01-29 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00008 | Survey/Enumeration assessment of unserved and underserved area and rural communities with no access to Electricity | Survey/Enumeration assessment of unserved and underserved area and rural communities with no access to Electricity | All LGAs | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-31 | 2025-01-30 | 52 | Not Started | 300000000 |  | 0 | 0 |  |  | Power - General
SPDO-MEE-P-23-00009 | Provision of Desktop/Laptop Computers and accessories for Technical and Statistics Staff of the Ministry | Provision of Desktop/Laptop Computers and accessories for Technical and Statistics Staff of the Ministry | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-02-01 | 2025-01-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MEE-P-23-00010 | Establish a standard Taraba State concrete pole industry and ring culvert | Establish a standard Taraba State concrete pole industry and ring culvert | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-02-02 | 2025-02-01 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00011 | Manpower Capacity Development on Technical Services (Transformer repair, re-winding etc) | Manpower Capacity Development on Technical Services (Transformer repair, re-winding etc) | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-02-03 | 2025-02-02 | 52 | Not Started | 800000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00012 | Drop-Down/Construction and installation of 15MVA 33/11Kv injection sub-station and 3No. 150Kva 11/0.415Kv at Taraba State Crushing and Asphalt plan Jalingo | Drop-Down/Construction and installation of 15MVA 33/11Kv injection sub-station and 3No. 150Kva 11/0.415Kv at Taraba State Crushing and Asphalt plan Jalingo | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-04 | 2025-02-03 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00013 | Provision for Feasibility study for all Mini, Small and large renewable energy resources in the State | Provision for Feasibility study for all Mini, Small and large renewable energy resources in the State | All LGAs | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-05 | 2025-02-04 | 52 | Not Started | 400000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00014 | Extension of 33KV line Mararaba-Bissa to Bissa, Kurmi town to the national grid | Extension of 33KV line Mararaba-Bissa to Bissa, Kurmi town to the national grid | Kurmi | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-06 | 2025-02-05 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00015 | Expansion and Construction Of Additional Mini Hydro-Electric Power Plant at Kakara Tea production Company | Expansion and Construction Of Additional Mini Hydro-Electric Power Plant at Kakara Tea production Company | Sardauna | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-07 | 2025-02-06 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00016 | Provision for Seminar, Economic Development and Energy training, and workshop for human capital development | Provision for Seminar, Economic Development and Energy training, and workshop for human capital development | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-08 | 2025-02-07 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00017 | Extension/Rehabilitation of 33kv line from Mararaba Mayo-Renewo village | Extension/Rehabilitation of 33kv line from Mararaba Mayo-Renewo village | Ardo-Kola | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-09 | 2025-02-08 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00018 | Provision of upgrading/Rehabilitation of all non-functional rural electrification stations in the state | Provision of upgrading/Rehabilitation of all non-functional rural electrification stations in the state | All LGAs | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-10 | 2025-02-09 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00019 | Extension of 33kv line to gassol town from mararraba Gassol and provision of TDN | Extension of 33kv line to gassol town from mararraba Gassol and provision of TDN | Gassol | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-11 | 2025-02-10 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00020 | Extension of 33kv line from wukari kente, with drop down at jende ikurlayi, ritti, igba and sondi | Extension of 33kv line from wukari kente, with drop down at jende ikurlayi, ritti, igba and sondi | Wukari | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-12 | 2025-02-11 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00021 | Provision of 650w Standalone solar system at Serti, Gembu, Bambur and Kumbo | Provision of 650w Standalone solar system at Serti, Gembu, Bambur and Kumbo | Sardauna, Karim-Lamido, Donga | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-13 | 2025-02-12 | 52 | Not Started | 1150000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00022 | Drop-down of 33kv line from Wukari and provision of TDN with 1Nos 300kva 33/0.415kv at Chonko Village Wukari LGA | Drop-down of 33kv line from Wukari and provision of TDN with 1Nos 300kva 33/0.415kv at Chonko Village Wukari LGA | Wukari | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-14 | 2025-02-13 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00023 | Extension of 33kv line from Wukari-Gida Idi with provision of TDN and 2No 300kva 33/0.415 transformer | Extension of 33kv line from Wukari-Gida Idi with provision of TDN and 2No 300kva 33/0.415 transformer | Wukari | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-15 | 2025-02-14 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00024 | Extension and installation of Electricity network in Jalingo metropolitan | Extension and installation of Electricity network in Jalingo metropolitan | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-16 | 2025-02-15 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00025 | Extension of 33Kv line from Bali Town-Garba Chede and construction of 7.5MVA injection substation with 4Nos Distribution Transformer | Extension of 33Kv line from Bali Town-Garba Chede and construction of 7.5MVA injection substation with 4Nos Distribution Transformer | Bali | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-17 | 2025-02-16 | 52 | Not Started | 700000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00026 | Provision of 6MW Standalone Solar town at Jalingo metropolitan and Government House | Provision of 6MW Standalone Solar town at Jalingo metropolitan and Government House | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-18 | 2025-02-17 | 52 | Not Started | 1500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00027 | Liaison with the Federal Ministry of Power, SCC, to connect to the surrounding communities from kashimbila to Takum to National grid | Liaison with the Federal Ministry of Power, SCC, to connect to the surrounding communities from kashimbila to Takum to National grid | Takum | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-19 | 2025-02-18 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00028 | Extension of 33Kv line from Kpambo to Fikyu town | Extension of 33Kv line from Kpambo to Fikyu town | Ussa | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-20 | 2025-02-19 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00029 | Extension of 33Kv line from Bali Serti town | Extension of 33Kv line from Bali Serti town | Bali | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-21 | 2025-02-20 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00030 | Extension of 132Kv line from Wukari to Jalingo and connection to main transmission line at Jalingo | Extension of 132Kv line from Wukari to Jalingo and connection to main transmission line at Jalingo | Wukari, Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-22 | 2025-02-21 | 52 | Not Started | 1500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00031 | Procurement of bulk transformers | Procurement of bulk transformers | All LGAs | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-23 | 2025-02-22 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00032 | Procurement of electrical consumables | Procurement of electrical consumables | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-24 | 2025-02-23 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00033 | Extension of 33Kv line from Donga to Tunari and TDN of Tunari | Extension of 33Kv line from Donga to Tunari and TDN of Tunari | Donga | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-25 | 2025-02-24 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00034 | Provision of 500Kw Solar energy at Damper Village. | Provision of 500Kw Solar energy at Damper Village. | Ibbi | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-26 | 2025-02-25 | 52 | Not Started | 600000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00035 | Rehabilitation of 33Kv line Zing LGA | Rehabilitation of 33Kv line Zing LGA | Zing | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-27 | 2025-02-26 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00036 | Extension of 33Kv line from Mayo-Lope to Abbare | Extension of 33Kv line from Mayo-Lope to Abbare | Lau | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-28 | 2025-02-27 | 52 | Not Started | 170000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00037 | Extension of 33Kv line from Hope afresh foundation to Government House and the surrounding | Extension of 33Kv line from Hope afresh foundation to Government House and the surrounding | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-02-29 | 2025-02-28 | 52 | Not Started | 120000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00038 | Procurement of 70T Crane Hiab | Procurement of 70T Crane Hiab | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-03-01 | 2025-03-01 | 52 | Not Started | 120000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00039 | Programme for Promoting Investment And Development of the Energy Sector | Programme for Promoting Investment And Development of the Energy Sector | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-03-02 | 2025-03-02 | 52 | Not Started | 240000000 |  | 0 | 0% |  |  | Power - General
SPDO-MEE-P-23-00040 | Development of Taraba State Economic Development Projects with ECOWAS | Development of Taraba State Economic Economic Development Projects with ECOWAS Bank of Investment and Development (EBID) Development Projects with ECOWAS Bank for Investment and Development (EBID) | Jalingo | Ministry of Energy and Economic Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-03-02 | 2025-03-02 | 52 | Ongoing | 1615000000 |  | 3091000000 | 191.4% |  |  | Power - General
SPDO-MFB-P-23-00001 | Purchase of 100No. Assorted Official Vehicles | Purchase of 100No. Assorted Official Vehicles | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4160000000.4 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00002 | Purchase of Office Stationeries & Equipment for State MDAs | Purchase of Office Stationeries & Equipment for State MDAs | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00003 | Capital Grants to Government Owned Companies | Capital Grants to Government Owned Companies | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00004 | Renovation and Remodelling of the Ministry of Finance, Budget and Economic Planning | Renovation and Remodelling of the Ministry of Finance, Budget and Economic Planning | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 800000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00005 | Construction of 3No. Sub-Treasuries (One Each) in Bali, Zing & K/Lamido | Construction of 3No. Sub-Treasuries (One Each) in Bali, Zing & K/Lamido | Bali, Zing & K/Lamido | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 202739450 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00006 | Renovation of 3No. Sub-Treasuries (One Each) in Takum, Wukari & Gembu | Renovation of 3No. Sub-Treasuries (One Each) in Takum, Wukari & Gembu | Takum, Wukari, Sarduna | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 99759915 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00007 | Drilling of 1No. Motorise Borehole at the Ministry of Finance, Budget & Planning | Drilling of 1No. Motorise Borehole at the Ministry of Finance, Budget & Planning | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3500000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00008 | Installation of CCTV Camera in the Ministry of Finance, Budget & Planning | Installation of CCTV Camera in the Ministry of Finance, Budget & Planning | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Security, Peace and Unity |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00009 | Five Fingers Agenda Coordination & Appraisal | Five Fingers Agenda Coordination & Appraisal | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MFB-P-23-00010 | Provision for Base Line Survey on Sustainable Development Goals | Provision for Base Line Survey on Sustainable Development Goals | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00011 | Monitoring and Evaluation of State Government Projects | Monitoring and Evaluation of State Government Projects | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Integrated supportive supervision
SPDO-MFB-P-23-00012 | Provision for the Establishment of State Single Register (SSR) | Provision for the Establishment of State Single Register (SSR) | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Data and data management
SPDO-MFB-P-23-00013 | Provision for Data Collection in the State (State Data Base Programme) | Provision for Data Collection in the State (State Data Base Programme) | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Decent Work and Economic Growth |  | Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Data and data management
SPDO-MFB-P-23-00014 | Coordinating State Nutrition Activities | Coordinating State Nutrition Activities | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 60000000 |  | 0 | 0% |  |  | Sustainable drug supply
SPDO-MFB-P-23-00015 | Provision for State Social Policy Development Plan | Provision for State Social Policy Development Plan | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MFB-P-23-00016 | Provision for Child Friendly Community Initiatives (CFCI) Programme in the State | Provision for Child Friendly Community Initiatives (CFCI) Programme in the State | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5000000 |  | 0 | 0% |  |  | Community interventions
SPDO-MFB-P-23-00017 | Construction of 1No. Office at the State Secretariat Complex | Construction of 1No. Office at the State Secretariat Complex | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MFB-P-23-00018 | Provisoon for Fund to Support Civil Society Organization (CSOs) | Provisoon for Fund to Support Civil Society Organization (CSOs) | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 25000000 |  | 0 | 0% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00019 | Sustainable Development Goals (SDGs) Projects | Sustainable Development Goals (SDGs) Projects | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 600000000 |  | 0 | 0% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00020 | Open Government Partnership (OGP) Project | Open Government Partnership (OGP) Project | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00021 | NG CARES Projects (Draw Down from IDA) | NG CARES Projects (Draw Down from IDA) | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3050989118.22 |  | 0 | 0% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00022 | Coodination of SABER (World Bank Assisted) Programme Activities in the State | Coodination of SABER (World Bank Assisted) Programme Activities in the State | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2024-01-01 | 30/04/2024 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00023 | Procurement of 208 Assorted Vehicles | For Government Officials, Security Agencies | All LGAs | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2024-01-01 | 30/04/2024 | 16 | Completed | 11598804949.11 |  | 11598804949.11 | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00024 | Preparation, Production, Dissemination of 2024 Budget and Staff Motivation | For the Day to Day Running of Government Activities | All LGAs | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 30/04/2024 | 16 | Completed | 61080000 |  | 61080000 | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00025 | Hostimg of 2023 Budget Implementation Report on Government Websites | For Donor Agencies to See and Key in Support | All LGAs | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2023-02-10 | 31/12/2023 | 12 | Completed |  |  |  | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00026 | Payment of Over N3B Counterpart Funding to FGN and World in the State | For Intervention in Education, Agriculture and Tourism | All LGAs | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2024-01-01 | 30/04/2024 | 16 | Completed | 3000000000 |  | 3000000000 | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00027 | Payment of Rented Quarters for Government Within and Outside the State Capital | Offices and Residential Accomodation | Others (Outside the state); | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2024-01-01 | 30/04/2024 | 16 | Completed | 632754500 |  | 632754500 | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00028 | Invitation of Raising Memo for the Payment Gratituities and Death Benefits to Retirees from 2011-2023 | To Cushion the Hardship After Serving the State for Over 30 Years | All LGAs | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 1000000000 |  | 1000000000 | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00029 | Payment of Over N1B for the Inventing of the Assorted Vehicles Purchased | To Indemnify in the Event of Theft, Accident and Damage | All LGAs | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 1092212898.22 |  | 1092212898.22 | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00030 | Loans From 4 Banks Over N200B Facilitated By the Ministry | ToFinance Government Projects/Programmes in Agric, Education | All LGAs | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2023-02-10 | 31/12/2023 | 12 | Completed |  |  |  | 100% |  |  | Poverty Alleviation - General
SPDO-MFB-P-23-00031 | Procurement of Vehicle | Official Use | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2026-01-01 | 31/12/2026 | 54 | Completed | 5150000000 |  | 434824500 | 100% |  |  | Reform of Government and Governance - General
SPDO-MFB-P-23-00032 | Purchase 2Nos JAC Hilux | Official Use | Jalingo | Ministry of Finance, Budget & Economic Planning | Ministry | Ministry |  |  | Economic and Job Creation |  | Partnerships for the Goals |  | 2026-01-01 | 31/12/2026 | 54 | Completed | 5150000000 |  | 205524950 | 100% |  |  | Reform of Government and Governance - General
SPDO-MHE-P-23-00001 | National Craft Expo, Abuja | A National Program aimed at promoting Cultural Heritage of our Dear state to attract both National and International Investors. | FCT Abuja | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  |  | 2024-09-09 | 1 | Not Started | 43373450 |  | 0 | 0% |  |  | Societal Re-orientation (General)
SPDO-MHE-P-23-00002 | Nwonyo Annual Fishing and Traditional Festival | To promote and preserve the cultural heritage and traditional fishing practices of the Nwonyo community, while attracting tourists, creating economic opportunities for local communities, and positioning Taraba State as a leading destination for cultural tourism. | Ibi | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-10-04 | 17/04/2026 | 1 | Completed | 250000000 |  | 250000000 | 100% |  |  | Societal Re-Orientation (General)
SPDO-MHE-P-23-00003 | Nwunyo Fishing Festival Development at Ibi LGA | A Proposed Project situated at RIVER IBBI for International Fishing festival, to attract Foreign Investors across the Globe. | Ibi | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Zero Hunger |  | 19/4/2023 | 21/04/2023 | 1 | Completed | 250000000 |  | 250000000 | 100% |  |  | Societal Re-orientation (General)
SPDO-MHE-P-23-00004 | National Festival of Arts & Culture (NAFEST) | A project Air Marked to showcase the Various Cultures we have in Nigeria. | FCT Abuja | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Economic Growth |  |  |  | 1 | Not Started | 72977875 |  | 0 | 0% |  |  | Societal Re-orientation (General)
SPDO-MHE-P-23-00005 | Provision for National Carnival, Abuja FCT | A project that Potrays Nigeria as one indivisible Entity, it involves displays of different Cultural background by all tribes in Nigeria. | FCT Abuja | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2023-12-08 | 2023-12-14 | 1 | Not Started | 30382300 |  | 0 | 0% |  |  | Societal Re-orientation (General)
SPDO-MHE-P-23-00006 | La Campagne Project | To develop a world-class tourism and hospitality destination that promotes eco tourism, cultural exchange, recreation, and investment, while leveraging Taraba State’s natural and cultural resources to drive sustainable tourism development. | Gashaka | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-06 | 31/12/2035 | 540 | Ongoing | 6800000000 |  | 300000000 | 4.412% |  |  | Societal Re-Orientation (General)
SPDO-MHE-P-23-00007 | National Festival of Arts and Culture (NAFEST) | To showcase and promote Taraba State’s diverse cultural heritage, traditional arts, crafts, music, dance, and indigenous traditions at the national level, while strengthening cultural exchange and tourism development. | Others (Outside the state); | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 22/11/2025 | 29/11/2025 | 7 | Completed | 125000000 |  | 125000000 | 100% |  |  | Societal Re-Orientation (General)
SPDO-MHE-P-23-00008 | International Arts and Crafts Expo (INAC) | To promote Taraba State’s indigenous arts, crafts and creative industries on an international platform, create market opportunities for local artisans, attract investment, and enhance the state’s visibility as a cultural and tourism destination. | Others (Outside the state); | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-09-10 | 2025-11-10 | 1 | Completed | 300000000 |  | 300000000 | 100% |  |  | Societal Re-Orientation (General)
SPDO-MHE-P-23-00009 | World Tourism Day | To celebrate and promote tourism in Taraba State by showcasing its rich natural, cultural and heritage attractions, increasing public awareness of the economic importance of tourism, and attracting tourists, investors and development partners. | Jalingo | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 27/09/2025 | 29/09/2025 | 1 | Completed | 135000000 |  | 135000000 | 100% |  |  | Societal Re-Orientation (General)
SPDO-MHE-P-23-00014 | Modern Multi - Purpose Cultural Centre in Jalingo | Multipurpose Center for Various Culture in Taraba State. | Jalingo State Capital | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Education |  | Education |  | 2023-01-04 | 2023-12-30 | 44 | Not Started | 95985700 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MHE-P-23-00019 | Taraba Carnival Programme in the State | Taraba Carnival Programme in the State | Jalingo; | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-09-30 | 36 | Not Started | 60382300 |  | 0 | 0% | No |  | Societal Re-Orientation (General)
SPDO-MHE-P-23-00022 | Establishment of Local Government Tourism Committee | Establishment of Local Government Tourism Committee | Jalingo; | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-09-30 | 36 | Not Started | 26382300 |  | 0 | 0% | No |  | Societal Re-Orientation (General)
SPDO-MHE-P-23-00036 | Feasibility Study, Documentation, Tourism Master Plan | Feasibility Study, Documentation, Tourism Master Plan | Jalingo | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-23 | 2025-03-23 | 52 | Not Started | 25000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MHE-P-23-00037 | Renovation of Mambilla Motel, Gembu | Renovation of Mambilla Motel, Gembu | Sardauna | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-24 | 2025-03-24 | 52 | Not Started | 37165025 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MHE-P-23-00038 | Promotional Material for State Tourism Board | Promotional Material for State Tourism Board | Jalingo | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-25 | 2025-03-25 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MHE-P-23-00039 | Tour Packaging in the State | Tour Packaging in the State | Jalingo | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-26 | 2025-03-26 | 52 | Not Started | 13191150 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MHE-P-23-00040 | Furnishing of Museum Gallery in the State | Furnishing of Museum Gallery in the State | Jalingo | Ministry of Heritage & Eco-Tourism | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-27 | 2025-03-27 | 52 | Not Started | 33191150 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-MHT-P-23-00001 | Construction of General Hospital | Construction of new general hospital Bali | Bali | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2025-12-01 | 28/02/2026 | 12 | Ongoing | 8788613938.33 |  | 4679146679.69 | 60% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00002 | Quality Assurance for Life Services | Monitoring and Supervision for quality services | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-11-20 | 30/06/2024 | 32 | Not Started | 5000000 |  | 0 | 0% |  |  | Community interventions
SPDO-MHT-P-23-00003 | Sexually Abused Referral Centre | Establishment of Center for treatment of Sexually Abuse persons | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Security, Peace and Unity |  | Reduced Inequality |  | 2023-12-01 | 2024-05-30 | 32 | Not Started | 95048000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00004 | National Health Information System | Improvement of Information and Data Gadgets | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Decent Work and Economic Growth |  | 2023-11-27 | 2024-05-30 | 28 | Not Started | 50000000 |  | 0 | 0% |  |  | Routine information system
SPDO-MHT-P-23-00005 | Solar Panel Housing in 4 General Hospitals | Solar Panel Housing in Four (4) General Hospitals | Wukari, Takum, Sardauna, Karim Lamido | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Affordable and Clean Energy |  | 2023-12-01 | 2024-06-30 | 28 | Not Started | 218000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00006 | Maternal and Parental Death Surveilance and Response (NPDSR) | Maternal and Parental Death Surveilance and Response (NPDSR) | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-06-30 | 24 | Not Started | 50000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00007 | Provision of Solar Powered Boreholes in 15 GH/CH | Provision of Solar Powered Boreholes in 15 GH/CH | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Affordable and Clean Energy |  | 2023-12-01 | 2024-06-30 | 28 | Not Started | 95974718 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00008 | Upgrade of Laboratory, Pharmacy & Theatre in 15No. GH/CH | Upgrading Laboratory, Pharmacy and Theatre of 15 General Hospital and First Referral Hospital | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-05-30 | 24 | Not Started | 41583500 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00009 | Logistic Management Commodity Unit (LMCU) (C-19) | Management of Commodities Logistics | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-05-30 | 24 | Not Started | 20000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00010 | Renovation of Specialist Hospital | Renovation and upgrade of Specialist hospital | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2025-12-01 | 28/02/2026 | 12 | Ongoing | 8484270689.53 |  | 2500000000 | 35% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00011 | State Strategic Health Development Plan | Development of state health strategic plan III | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-12-01 | 2024-05-30 | 24 | Not Started | 10000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MHT-P-23-00012 | Blood Bank/Blood Transfusion Services | Blood bank servece an laboratory | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-05-30 | 24 | Not Started | 8000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00013 | Laboratory Quality Management System (QMS) Implementation (Lab) | Medical Laboratory quality management system | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-06-30 | 28 | Not Started | 8000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00014 | Scale Up TB Control Programme to all Health Facilities | Testing and treatment of tuberclosis | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-06-30 | 28 | Not Started | 10000000 |  | 0 | 0% |  |  | Sustainable drug supply
SPDO-MHT-P-23-00015 | Diseases Surveilance and Response (C-19) | Surveillance reporting and treatment of disease outbreak | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 20 | Not Started | 10000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00016 | Onchocerciasis and blindness control | Advocacy, treatment and drugs supply of Onchocerciasis and blindness control | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-01-12 | 2024-08-31 | 32 | Not Started | 8000000 |  | 0 | 0% |  |  | Community interventions
SPDO-MHT-P-23-00017 | Procurement of Ambulance to Secondary Health Facilities (C-19) | Procurement of Ambulances Vehicles to Secondary health facilicties | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-07-31 | 32 | Not Started | 50000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00018 | Purchase of Essential Drugs and Medical Equipment in the State | Procurement and Distribution of essential drugs to various health facilities | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-10-09 | 2024-04-30 | 24 | Not Started | 50000000 |  | 0 | 0% |  |  | Sustainable drug supply
SPDO-MHT-P-23-00019 | Renovation of General Hospital, Takum | Renovation and Equipping of General hospital Takum | Takum | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Industry, Innovation and Infrastructure |  | 2021-02-09 | 2025-12-07 | 24 | Ongoing | 570462213.09 |  | 475547201.7 | 83.36% |  |  | Functional health facilities
SPDO-MHT-P-23-00020 | College of Nursing and Midwifery | Renovation and upgrade of College of Nursing and Midwifery | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2025-12-01 | 28/02/2026 | 12 | Ongoing | 11100000000 |  | 11100000000 | 100% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00021 | Research and Development for Health Sector Programme in the State | Research and Development for Health Sector Programme in the State | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2023-12-01 | 2024-06-30 | 28 | Not Started | 10000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00022 | Construction of General Hospital Lissam | Construction and Equipping of General Hospital Lissam | Ussa | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2025-12-01 | 28/02/2026 | 12 | Completed | 2996327825.87 |  | 2996327825.87 | 100% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00023 | Coordination of Nutrition Activities | Coordination of Nutrition Activities | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 27/11/2023 | 2024-05-30 | 28 | Not Started | 50000000 |  | 0 | 0% |  |  | Community interventions
SPDO-MHT-P-23-00024 | Provision for Upgrading of First Referel Hospital Donga to General Hospital | Provision for Upgrading of First Referel Hospital Donga to General Hospital | Donga | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-11-08 | 2024-05-15 | 36 | Ongoing | 1080246024.45 |  | 600000 | 45% |  |  | Functional health facilities
SPDO-MHT-P-23-00025 | Furniture & Fixtures | Purchase of furniture for facilities and Ministry | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2025-12-01 | 28/02/2026 | 12 | Ongoing | 20795135089.56 |  | 2000000000 | 9.618% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00026 | Construction of FRH Kona | Construction and Equipping FRH Kona | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2025-12-01 | 28/02/2026 | 12 | Ongoing | 500000000 |  | 100000000 | 20% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00027 | Reconstruction of CHC Gindin Waya, Ibi LGA | Reconstruction and eqiping of CHC ginding waya | Ibi | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-06-30 | 28 | Not Started | 98048000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00028 | Rehabilitation of Hospitals: Ibi, Baissa | Rehabilitation of Hospitals: Ibi, Baissa | Ibi, Kurmi | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-13 | 2024-08-13 | 36 | Not Started | 2000000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00029 | Construction of Staff Qtrs in 3 Referral Hosp. (Pantisawa, Serti & M/Biyu) | Construction of Staff Qtrs in 3 Referral Hosp. (Pantisawa, Serti & M/Biyu) | Yorro, Sardauna, Gassol | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Decent Work and Economic Growth |  | 2024-04-10 | 2024-10-22 | 32 | Not Started | 178215000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00030 | Completion of First Referral Hospital, Lissam | Completion of the construction FRH Lissam | Ussa | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-10-26 | 2024-05-22 | 36 | Ongoing | 6000000000 |  | 2996327825.87 | 95% |  |  | Functional health facilities
SPDO-MHT-P-23-00031 | Provision of 3No. Mobile Clinic in the State | Purchase and equipping of mobile clinic | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-20 | 2024-05-15 | 32 | Not Started | 600000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00032 | Procurement Hospital Equipmemt and Consumables | Supply of medical equipment and consumables for hospitals | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-11-22 | 2024-05-22 | 30 | Not Started | 272500000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00033 | Renovation of Offices, Provision Equipment and Furniture | Renovation of Offices, Provision Equipment and Furniture | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Decent Work and Economic Growth |  | 2023-12-20 | 2024-06-11 | 26 | Not Started | 109000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00034 | Constructing & Equipping of Public Health Labs & Epid Unit | Construction and equipping public health laboratory | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-11-21 | 2024-07-24 | 33 | Not Started | 218000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00035 | Renovation of General Hospital, Gembu | Renovation and equiping of General Hospital Gembu | Sardauna | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Decent Work and Economic Growth |  | 2023-12-01 | 2024-05-30 | 24 | Not Started | 450000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00036 | Furnishing & Equipping of the College Laboratory | Furnishing & Equipping of the College Laboratory | Takum | Ministry of Health | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2023-12-01 | 2024-05-30 | 24 | Not Started | 5000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00037 | Renovation of General Hospital, Bali | Renovation and Equiping of General Hospital Bali | Bali | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-11-20 | 2024-08-31 | 38 | Not Started | 1000000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00038 | Renovation of General Hospital, Wukari | Renovation and equiping of General Hospital Wukari | Wukari | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2023-06-30 | 28 | Not Started | 1200000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00039 | Construction /Equipping Gh Karim, Karim – Lamido | To bring qualitative health care closer to the people | Karim Lamido | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2025-12-01 | 2026-06-30 | 28 | Ongoing | 35000000000 |  | 21000000000 | 60% |  |  | Functional health facilities
SPDO-MHT-P-23-00040 | Renovation of General Hospital, Zing | Renovation and Equiping of General Hospital Zing | Zing | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-01 | 2024-08-31 | 38 | Not Started | 1800000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00041 | Renovation & Upgrading of College of Health Technology, Takum | Renovation & Upgrading of College of Health Technology, Takum | Takum | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-12-20 | 2024-08-20 | 37 | Ongoing | 2172357983.57 |  | 350000000 | 16.11% |  |  | Functional health facilities
SPDO-MHT-P-23-00042 | Installation of Magnetic Resonate Images in Takum, Wukari, Bambur& Gembu Hopspitals | Installation of Magnetic Resonate Images in Takum, Wukari, Bambur& Gembu Hopspitals | Takum, Wukari, Karim-Lamido, Sardauna | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-11-15 | 2024-06-20 | 30 | Not Started | 436000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00043 | Construction of Basic Health Care Clinic at Mambila Estate Kakara, Sardauna LGA | Construction of Basic Health Care Clinic at Mambila Estate Kakara, Sardauna LGA | Sardauna | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-10-31 | 2024-07-16 | 36 | Not Started | 92650000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00044 | Construction of college of Nursing and midwifery Jalingo | Construction of college of college of Nursing and midwifery Jalingo | Jalingo; | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-09-21 | 2024-09-21 | 56 | Ongoing | 7000000000 |  | 4000000000 | 57.14% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00045 | Procurement of 175No. Tricycle Ambulances | Procurement of 175No. Tricycle Ambulances | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-03 | 2025-03-03 | 52 | Ongoing | 1050000000 |  | 20000000 | 2% |  |  | COVID-19 - General
SPDO-MHT-P-23-00046 | Purcahse of Drugs and Medicines, Hospital Consumables | Drugs was distributed across public hospitals to improve treatment services within the State | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2023-01-06 | 30/10/2023 | 20 | Completed | 35000000 |  | 35000000 | 100% |  |  | Improvement to Human Health
SPDO-MHT-P-23-00047 | Oxygen Plants | Oxygen Plants | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-04 | 2025-03-04 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00048 | Construction of Primary Health Care Centre at Manang, Yorro LGA | Construction of Primary Health Care Centre at Manang, Yorro LGA | Yorro | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-05 | 2025-03-05 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00049 | Medical Assistance to State Indigents Persons | Medical Assistance to State Indigents Persons | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-06 | 2025-03-06 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Community interventions
SPDO-MHT-P-23-00050 | Equipping of Renovated General Hospitals | Equipping of Renovated General Hospitals | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-07 | 2025-03-07 | 52 | Not Started | 218000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00051 | Completion of College of Nursing & Midwifery | Fittings/Equipment for College of Nursing & Midwifery | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Industry, Innovation and Infrastructure |  | 2024-03-08 | 2025-03-08 | 52 | Ongoing | 500000000 |  | 100000000 | 20% |  |  | Functional health facilities
SPDO-MHT-P-23-00052 | Provision for State Council on Health Programme in the State | Provision for State Council on Health Programme in the State | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-09 | 2025-03-09 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MHT-P-23-00053 | Conduct of Partners Forum Meeting & Other TWGs Meetings | Conduct of Partners Forum Meeting & Other TWGs Meetings | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-10 | 2025-03-10 | 52 | Not Started | 5000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-MHT-P-23-00054 | Hospital Labs and Hospital Theatre Consumables | Hospital Labs and Hospital Theatre Consumables | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-11 | 2025-03-11 | 52 | Not Started | 70000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00055 | Provision for Covid - 19 Response | Provision for Covid - 19 Response | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-12 | 2025-03-12 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MHT-P-23-00056 | Renovation of First Referral Hospital in the State | Renovation of First Referral Hospital in the State | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-13 | 2025-03-13 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00057 | Procurement of 3No. Mobile Clinic | Procurement of 3No. Mobile Clinic | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-14 | 2025-03-14 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00058 | Construction of Specialist Hospital at Wukari Town | Construction of Specialist Hospital at Wukari Town | Wukari | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-15 | 2025-03-15 | 52 | Not Started | 2000000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00059 | Renovation of Central Medical Store | Renovation of Central Medical Store | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-16 | 2025-03-16 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00060 | Suport to hard to reach area project community | Suport to hard to reach area project community | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-17 | 2025-03-17 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Community interventions
SPDO-MHT-P-23-00061 | WHO Health Project | WHO Health Project | All LGAs | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-18 | 2025-03-18 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00062 | Contruction of TSCHIA | Contruction of TSCHIA | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-03-19 | 2025-03-19 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00063 | Skill Acquisition Centre in College of Nursing Jalingo | Skill Acquisition Centre in College of Nursing Jalingo | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Women and Youth Empowerment |  | No Poverty |  | 2024-03-20 | 2025-03-20 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00064 | CBT Centre College of Health Technology Takum | CBT Centre College of Health Technology Takum | Takum | Ministry of Health | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-03-21 | 2025-03-21 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-MHT-P-23-00065 | Counter part fund for S Map T Blind | Counter part fund for S Map T Blind | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-22 | 2025-03-22 | 52 | Not Started | 446000000 |  | 0 | 0% |  |  | Counter part fund for S Map T Blind
SPDO-MHT-P-23-00066 | Renovation/remodeling of FRH Donga, Donga LGA | Renovation/remodeling of FRH Donga, Donga LGA | Donga | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2026-01-01 | 2026-07-31 | 28 | Ongoing | 1080246024.45 |  | 300000000 | 27.77% |  |  | Functional health facilities
SPDO-MHT-P-23-00071 | PROCUREMENT OF DENTAL EQUIPMENT FOR DENTAL CLINIC UNIT AT SPECIALIST HOSPITAL JALINGO | To bring qualitative health care closer to the people | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-01 | 31/12/2025 | 54 | Completed | 704774139.19 |  | 609756097.56 | 100% |  |  | Functional health facilities
SPDO-MHT-P-23-00067 | Renovation/remodeling of Specialist Hospital Jalingo | Renovation/remodeling of Specialist Hospital Jalingo | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2026-01-01 | 2026-07-31 | 28 | Ongoing | 8484270689.53 |  | 2500000000 | 29.47% |  |  | Functional health facilities
SPDO-MHT-P-23-00070 | RENOVATION/REMODELING OF DENTAL CLINIC UNIT AT SPECIALIST HOSPITAL JALINGO | To bring qualitative health care closer to the people | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-01 | 31/12/2025 | 54 | Completed | 135311941.63 |  | 200000000 | 100% |  |  | Functional health facilities
SPDO-MHT-P-23-00068 | CT – SCAN | To bring qualitative health care closer to the people | Jalingo | Ministry of Health | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-01 | 31/12/2025 | 54 | Ongoing | 1626688000 |  | 1109756097.56 | 80% |  |  | Functional health facilities
SPDO-MHT-P-23-00069 | General Hospital Warwar | To bring qualitative health care closer to the people | Sardauna | Ministry of Health | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2025-01-01 | 31/12/2025 | 54 | Ongoing | 1887192902.07 |  | 800000000 | 40% |  |  | Functional health facilities
SPDO-MIR-P-23-00001 | Procurement of Heideberg SM 74 (A2 Size) 5 Color Machine with Larker Unit for GPP | Procurement of Heideberg SM 74 (A2 Size) 5 Color Machine with Larker Unit for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 135000000 |  | 0 | 0% | No |  | Information Communication and Technology - General
SPDO-MIR-P-23-00002 | Procurement of Polar Cutting Machine (115) for GPP | Procurement of Polar Cutting Machine (115) for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 28000000 |  | 0 | 0% | No |  | Ministry of Information & Re - Orientation
SPDO-MIR-P-23-00003 | Procurement of MOZ 2 Color Machine for GPP | Procurement of MOZ 2 Color Machine for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 62000000 |  | 0 | 0% | No |  | Information Communication and Technology - General
SPDO-MIR-P-23-00004 | Procurement of Folding Machine (A1 Size) for GPP | Procurement of Folding Machine (A1 Size) for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% | No |  | Information Communication and Technology - General
SPDO-MIR-P-23-00005 | Purchase of Industrial Laminating Machine for GPP | Purchase of Industrial Laminating Machine for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-04-30 | 52 | Not Started | 15000000 |  | 0 | 0% | No |  | Information Communication and Technology - General
SPDO-MIR-P-23-00006 | Procurement of Baby Pony Binding Machine for GPP | Procurement of Baby Pony Binding Machine for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-08-31 | 52 | Not Started | 35000000 |  | 0 | 0% | No |  | Information Communication and Technology - General
SPDO-MIR-P-23-00007 | Purchase of Sttiching Machine for GPP | Purchase of Sttiching Machine for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5000000 |  | 0 | 0% | No |  | Information Communication and Technology - General
SPDO-MIR-P-23-00008 | Procurement of Direct Imaging Machine Printing Machine for GPP | Procurement of Direct Imaging Machine Printing Machine for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00009 | Graphics Design Workstation for GPP | Graphics Design Workstation for GPP | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 70000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00010 | 8 HD Camerars for TTV | 8 HD Camerars for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 144000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00011 | Lighting Equipment for TTV | Lighting Equipment for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 9000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00012 | Video Mixer for TTV | Video Mixer for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 27000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00013 | 10 Audio Microphones for TTV | 10 Audio Microphones for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-06-30 | 52 | Not Started | 9000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00014 | Audio Mixer for TTV | Audio Mixer for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-08-31 | 52 | Not Started | 3600000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00015 | 2 Video Matrix Display Wall (20fit x 10ft) for TTV | 2 Video Matrix Display Wall (20fit x 10ft) for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-03-31 | 52 | Not Started | 90000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00016 | 3 Recording Studio Setup for TTV | 3 Recording Studio Setup for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-06-30 | 52 | Not Started | 270000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00017 | News Desk Remodel for TTV | News Desk Remodel for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 36000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00018 | OB Van with Internet Sitelite Connectivity for TTV | OB Van with Internet Sitelite Connectivity for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-03-31 | 52 | Not Started | 180000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00019 | Outdoor Camerars for TTV | Outdoor Camerars for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 57600000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00020 | 4 Wireless Microphones for TTV | 4 Wireless Microphones for TTV | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2880000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00021 | Live Studio Setup for TSBS | Live Studio Setup for TSBS | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 118000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00022 | 2 Recording Studio Setup for TSBS | 2 Recording Studio Setup for TSBS | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 144000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00023 | 4 Studio Camerars for Streaming in TSBS | 4 Studio Camerars for Streaming in TSBS | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 18000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00024 | 3 Audio Mixers for TSBS | 3 Audio Mixers for TSBS | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10800000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00025 | 10 Microphone for TSBS | 10 Microphone for TSBS | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5400000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00026 | Purchase of 20No. Laptops/Desk Stop Computer and Accessories | Purchase of 20No. Laptops/Desk Stop Computer and Accessories | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Information Communication and Technology - General
SPDO-MIR-P-23-00027 | Printing of Diaries, Calendars & Paper Handbags | Educative and Research Purposes | Jalingo | Ministry of Information and Re-Orientation | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-01-12 | 31/12/2023 | 4 | Completed | 49,000,000:00 |  | 49,000,000:00 | 100% |  |  | Information Communication and Technology - General
SPDO-MJT-P-23-00001 | Construction of 1No. Office Complex and Furniture in Jalingo | Construction of the Ministry Headquarters | All LGA's | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MJT-P-23-00002 | Purchase of Law Books & Journals | Purchase of Law Books & Journals | All LGA's | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 50000000 |  | 1500000 | 3% |  |  | Libraries and laboratories
SPDO-MJT-P-23-00003 | Establishment of Multi - Door Court | Establishment of Multi - Door Court | All LGA's | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00004 | Sattlement of outstanding Judgement Debt | Sattlement of outstanding Judgement Debt | All LGA's | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 400000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00005 | Witness Support Fund | Witness Support Fund | All LGA's | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00006 | Council for Prevogative of Mercy | Council for Prevogative of Mercy | Jalingo, Wukari, Sardauna, Gassol, Zing, Bali, Gashaka, Takum, Kurmi | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 13500000 |  |  | 0% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00007 | Codification and Review of Laws of Taraba State | Codification/Laws Review and Law Books Purchase of Taraba State from 1991 to Date | Jalingo | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-10-01 | 31/12/2024 | 52 | Not Started | 50000000 |  |  | 0% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00008 | Implementation of Executive Order No. 5 | Implementation of Executive Order No. 5 on Mining Regulations | Jalingo | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2023-01-10 | 31/12/2024 | 52 | Completed | 16000000 |  | 16000000 | 100% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00009 | Construction of the Ministry Headquarters | Construction of the Ministry Headquarters in Jalingo | Jalingo | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 31/12/2024 | 52 | Ongoing | 350000000 |  | 40000000 | 11% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00010 | Construction of Honourable Attorney-General’s Chambers within the State Secretariat | Construction of Honourable Attorney-General’s Chambers within the State Secretariat | Jalingo | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 31/12/2024 | 4 | Ongoing | 702218191.88 |  | 200000000 | 28.48% |  |  | Reform of Government and Governance - General
SPDO-MJT-P-23-00011 | NIGERIAN LAW SCHOOL YOLA CAMPUS | STUDENTS' HOSTEL | Others (Outside the state); | Ministry of Justice | Ministry | Ministry |  |  | Security, Peace and Unity |  | Peace, Justice and Strong Institutions |  | 2025-01-10 | 30/10/2025 | 4 | Ongoing | 989861539.51 |  | 550000000 | 55.56% |  |  | Reform of Government and Governance - General
SPDO-MNP-P-23-00001 | Take-off Grand for the Ministry To renovate and Furnish the office space at TSUBEB former office at Kasuwan Yelwa, Jalingo. | To create a conducive environment for its staff | Jalingo | Ministry of Nuresery & Primary Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 25/07/2026 | 24/08/2026 | 4 | Ongoing | 120000000 |  | 73645000 | 80% |  |  | Early Childhood Care, Development and Education (ECCDE)
SPDO-MNP-P-23-00002 | Construction of 1000 units of pupils desk for distribution to public primary schools and transportation to various destination | To create a conducive environment for its staff | All LGAs | Ministry of Nuresery & Primary Education | Ministry | Ministry |  |  | Education |  | Quality Education |  | 18/07/2026 | 24/08/2026 | 4 | Ongoing | 37000000 |  | 30000000 | 80% |  |  | Early Childhood Care, Development and Education (ECCDE)
SPDO-MRU-P-23-00001 | Rural Electrification of communities in the state | Rehabilitation & Upgrading of Nguroje Electric Project | Sardauna | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 1/1/202 | 2024-12-31 | 52 | Not started | 350000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00014 | Construction of Five (5) Culvert in Zangon Kombi Ward Ardo-Kola | Rural Road construction | Ardo-Kola | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00015 | Construction of Culvert at Fete Community in Takum | Rural road construction | Takum | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00019 | Construction of Ten (10) New Culvert in Taka Lafiya Ward Bali | Rural road construction | Bali | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00026 | Construction of 12Km Feeder Road from Misheli-Buding Lau | Rural Road construction | Gashaka | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00031 | Supply of Istallation 230KV Solar Energy at General Hospital | Rural electrification | Karim Lamido | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Healthcare |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00032 | Construction of market store building at Jen town, K/Lamido | Rural Constructions | Karim Lamido | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00039 | Fencing of cattle Market at Andemi Town Karim-Lamido | Rural Constructions | Karim Lamido | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00047 | Construction of Market and Shed at Dolla Town, Lau LGA | Rural Constructions | Lau | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00051 | Construction of town hall Building Danbeki Town, kurmi LGA | Rural road construction | Kurmi | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00054 | Extension/Rehabilitation of 33kV line to Mayo Ranewo | Rural road construction | Ardo Kola | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00055 | renovation and Upgrading of Jen Electrification | Rural electrification | Karim Lamido | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00057 | Extension of 33KV/ITC line from Wukari-Gidan Dorowa Wukari | Rural electrification | Wukari | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00062 | Electronic Bill Board in Jalingo | Rural road construction | Ardo Kola | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00063 | Extension of 33kKVA line (DTN) from Marraraba Baissa to Baissa | Rural electrification | Kurmi | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00064 | Procurement of 20No. Transformers for distribution LGA | Rural electrification | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Completed | 100000000 |  | 200000000 | 100% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00066 | Construction of Skill Acquisition Centre at Dorofi, Gembu Town | Rural construction | Gembu | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00067 | Supply and Istallation of 4Nos. 300KVA 33/0.415 at Baissa | Rural electrification | Takum | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00068 | Electronic Bill Board in Jalingo | Urban development | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00074 | Public Awareness on Sanitation and Personal Hygiene | Urban development | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Education |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00075 | Provision Urban Renewal Programme | Urban development | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00076 | Construction of Jalingo ArdoKola RD (18KM) | Rural road construction | Jalingo, Ardo-Kola | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00077 | Bobboji drainage Storm Water II | Rural road construction | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Good Health and Well-being |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00078 | Construction of Roads in the Rural Communities of all LGAs in the State | Rural road construction | All LGAs | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 350000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00079 | Construction and Maitainance of Township Roads | Rural road construction | All LGAs | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00080 | Street Naming and House Numbering | Rural road construction | All LGAs | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00081 | Construction of Roundabout | Rural road construction | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00082 | Construction of Roads in New Government Layouts | Rural road construction | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00083 | Extension of Electricity from Lissam - Rufu Town | Urban development | Ussa | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00084 | Solar Street Light in Vakude, Kara, Mbar, Clona & Song Bariki in Sardauna L.G.A | Urban development | Sardauna | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00085 | Solar Street Light in Titong, Lakitoba, Mbaso, Lame Tella, Gembu, Mayo-Ndaga & Kon-Iyaka | Urban development | Sardauna | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Affordable and Clean Energy |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00086 | Feeder Road from Gembu-Mbela to Dorofi Mbela-Kara to Song Bariki Vakude-Dorofi | Rural road construction | Sardauna | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00087 | Feeder Road 13KM from Lekitaba-Ngubiri to Mbeso Road & from Gembu Science School to Lome fuel 7KM Road | Rural road construction | Sardauna | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 45000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00088 | 10 Lock-up Shops at Kan-Iyaka, Nyamban, Kuma and Lame Bora | Rural road construction | Sardauna | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00089 | Construction of Feeder Road from Local Government Secretariat to Sabon Layi to GSS Bali | Rural road construction | Bali | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 45000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00090 | Construction of Feeder Road & Culvert Yelwan Abbare Road Jalingo | Rural road construction | Jalingo | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00091 | Drilling of Ten (10) Borehole in Ten (10) Wards of Ardo Kola | Urban development | Ardo Kola | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00092 | Construction of PHC in Tau, Iware, Ranti & Ardo Kola Ward Basa | Rural road construction | Ardo Kola | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 40000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00093 | Construction of 12Km Feeder Road from Misheli-Buding Lau | Rural road construction | Lau | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MRU-P-23-00094 | Construction of Feeder Road from Government Lodge to Bonke Bali | Rural road construction | Bali | Ministry of Rural & Urban Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Housing and Urban Development - General
SPDO-MSJ-P-23-00001 | Renovation and furnishing of Area Social Justice and Re-Integration offices in Wukari, and Gembu | To enable our Area Office staff work conductively and also generate more revenue to the Government Treasury. | Wukari, Sardauna | Ministry Social Justice & Re-Integration | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-01-09 | 30/11/2024 | 12 | Completed | 189745539 |  | 63439106.99 | 100% |  |  | Societal Re-orientation - General
SPDO-MSJ-P-23-00002 | Construction of IDP Centre in Karim Lamido, Bali & Ussa | Construction of IDP Centre inKarim-Lamido, Bali and Ussa | Karim Lamido;Bali;Ussa; | Ministry Social Justice & Re-Integration | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Reduced Inequality |  | 2024-02-01 | 2024-12-31 | 48 | Not Started | 420000000 |  | 0 | 0% | No
SPDO-MSJ-P-23-00003 | Care for The Destitute | Care for the refugee or stranded visitors, and Nnn indegen that are stranded to be relocated back to their state of origin. | All LGAs; | Ministry Social Justice & Re-Integration | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 75205166 |  | 0 | 0% | No |  | Societal Re-orientation - General
SPDO-MSJ-P-23-00004 | Construction of Rehabilitation Centre of PWDs in Jalingo, Wukari & Gassol | Construction of Rehabilitation Centre of People With Disabilities In Jalingo, Wukari and Gassol | Jalingo;Wukari;Gassol; | Ministry Social Justice & Re-Integration | Ministry | Ministry |  |  | Economic and Job Creation |  | Reduced Inequality |  | 2024-01-01 | 2024-11-30 | 48 | Not Started | 300000000 |  | 0 | 0% | No |  | Societal Re-orientation - General
SPDO-MSJ-P-23-00005 | Construction of Recreational Centre for the Aged/Elderly Persons | Construction of Recreation Centre for the Aged/elderly Persons | All LGAs; | Ministry Social Justice & Re-Integration | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-11-30 | 48 | Not Started | 90000000 |  | 0 | 0% | No |  | Societal Re-orientation - General
SPDO-MSJ-P-23-00006 | Renovation & Maintenance of Area Office in the State | Construction and Furnishing of 13 Area offices in Jalingo, Ardo-kola, Zing, Yoro, Lau, Gassol, Gashaka, Kurmi, Bali, Ussa, Karim-lamido, Donga and Ibi | Ardo-kola;Bali;Donga;Gashaka;Gassol;Ibi;Jalingo;Karim Lamido;Kurmi;Lau;Ussa;Yorro;Zing; | Ministry Social Justice & Re-Integration | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-12-01 | 2024-06-30 | 52 | Not Started | 86000000 |  | 0 | 0% | Yes | From License payment of Hotels, Pool betting, Snookers | Societal Re-orientation - General
SPDO-MSS-P-23-00001 | Stockpilling of Relief Materials | Humanitarian Assistance to Disaster Victims | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 238390000 |  | 8000000 | 3.3% |  |  | COVID-19 - General
SPDO-MSS-P-23-00002 | Coordination of Disasters | Coordination of Disasters | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MSS-P-23-00003 | Rehabilitation and Inclusion of Persons with Disabilities | Rehabilitation and Inclusion of Persons with Disabilities | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Reduced Inequality |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MSS-P-23-00004 | Disaster Management in the State | Disaster Management in the State | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Reduced Inequality |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MSS-P-23-00005 | Provision for the Less Privilege and Vulnerable People in the State | Provision for the Less Privilege and Vulnerable People in the State | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Reduced Inequality |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 26000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MSS-P-23-00006 | Provision for Social Integration & Community Development | Provision for Social Integration & Community Development | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Reduced Inequality |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MSS-P-23-00007 | Provilsion for Partnership with Non Governmental Organization & Stakeholders | Provilsion for Partnership with Non Governmental Organization & Stakeholders | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 29138116 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MSS-P-23-00008 | Assistance to Fire Disaster Victims in the State | Assistance to Fire Disaster Victims in the State | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MSS-P-23-00009 | Formation of Peace & Reconciliation in Communities in the State | Formation of Peace & Reconciliation in Communities in the State | All LGA's | Ministry of Special Duties & Social Services | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-MST-P-23-00001 | Construction of technology village (phase1) | To develop strong knowledge base that will contribute to Nigeria's economic dependency and help in job creation | Jalingo; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-22 | 2024-07-30 | 24 | Not Started | 3000000 |  | 0 | 0% | Yes | It will help in generating revenue by providing scientific inventions and other services to be sold | Information Communication and Technology (General)
SPDO-MST-P-23-00002 | Science Technology and Innovation (STI) Policy | Policy formulation for the ministry | Jalingo; | Ministry of Science & Technology | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Industry, Innovation and Infrastructure |  | 2024-01-10 | 2024-04-10 | 13 | Not Started | 67000000 |  | 0 | 0% | No |  | Information Communication and Technology (General)
SPDO-MST-P-23-00003 | Tissue culture/ fish pond and feeds production | Tissue culture production, fish farming and feeds | Jalingo; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-02-05 | 2024-06-05 | 18 | Not Started | 30000000 |  | 0 | 0% | Yes | Tissue culture and feeds production are sold thereby helping in the growth of the GDP | Information Communication and Technology (General)
SPDO-MST-P-23-00004 | Construction of biotechnology agency (Phase1) | Construction of an agency for biotechnology | Jalingo; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-08 | 2024-08-08 | 33 | Not Started | 650000000 |  | 0 | 0% | Yes | Economic development | Information Communication and Technology (General)
SPDO-MST-P-23-00005 | National council/ expos/ 774 young NPA 2024 | National and state science expos for science students and exhibitions | All LGAs;Others (Outside the state); | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-02-10 | 2024-12-15 | 49 | Not Started | 12518000 |  | 0 | 0% | No |  | Information Communication and Technology (General)
SPDO-MST-P-23-00006 | GSM/ mobile app tech/ welding and fabrications/ advance manufacturing technology (capacity building) | Local and software manufacturing | Jalingo; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-02-28 | 2023-07-28 | 21 | Not Started | 37000000 |  | 0 | 0% | Yes | It tends to generate huge revenue for the state | Information Communication and Technology (General)
SPDO-MST-P-23-00007 | World science day/STEM/partnership | World science day exhibition | All LGAs;Others (Outside the state); | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-03-05 | 2024-08-05 | 22 | Not Started | 10000000 |  | 0 | 0% | No |  | Information Communication and Technology (General)
SPDO-MST-P-23-00008 | Technoprenuership cosmetology/ renewable energy tech/STI culture and live stock fishery | Sustainability in the use of renewable energy, recycling and livestock farming | Jalingo; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Responsible Consumption & Production |  | 2024-02-05 | 2024-06-05 | 22 | Not Started | 31000000 |  | 0 | 0% | Yes | When product are sold will increase the state IGR | Information Communication and Technology (General)
SPDO-MST-P-23-00009 | Procurement of machines for processing and packaging | Purchase of machines for the agencies and technology village | Jalingo;Ardo-kola;Yorro; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-10 | 2024-04-05 | 12 | Not Started | 27508000 |  | 0 | 0% | Yes | Help in the production of different quality items to be sold | Information Communication and Technology (General)
SPDO-MST-P-23-00010 | Basic Science Kits | Provision of Science Equipments in schools | All LGAs | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2023-01-11 | 2024-01-01 | 12 | On hold | 83783999.6 |  | 40000000 | 48% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MST-P-23-00011 | Construction of chemical technology development agency ( phase1) | Construction of chemical agency | Ardo-kola; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-08 | 2024-08-08 | 33 | Not Started | 750000000 |  | 0 | 0% | Yes | Promotes research and economic development | Information Communication and Technology (General)
SPDO-MST-P-23-00012 | Leather work/ fertilizer/fruit processing and packaging | Processing and packaging of fruits and fertilizers | Ardo-kola; | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-05 | 2024-08-08 | 25 | Not Started | 40000000 |  | 0 | 0% | Yes | Profit making activity | Information Communication and Technology (General)
SPDO-MST-P-23-00013 | Science Kits | To equip selected science senior secondary schools across with state with modern day up-todate science kits for laboratories. | All LGAs | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/03/2024 | 12 | Ongoing | 82000000 |  | 40000000 | 40% |  |  | Information Communication and Technology (General)
SPDO-MST-P-23-00014 | JETS | To promote Engineering, Technology and Science in Primary and Secondary schools. | All LGAs | Ministry of Science & Technology | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 30000000 |  | 30000000 | 100% |  |  | Information Communication and Technology (General)
SPDO-MST-P-23-00015 | YSPA | To identify young talents among students in the state and country at large | All LGAs | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/03/2024 | 12 | Completed | 5700000 |  | 5700000 | 100% |  |  | Information Communication and Technology (General)
SPDO-MST-P-23-00016 | AI Conference in Borno State | To acquire background knowledge of AI | Others (Outside the state); | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-01-01 | 31/03/2024 | 12 | Completed | 5400000 |  | 5400000 | 100% |  |  | Information Communication and Technology (General)
SPDO-MST-P-23-00017 | National Science, Technology and Innovation Expo | To showcase STI among states, MDAs and NGOs. | All LGAs | Ministry of Science & Technology | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 31/03/2024 | 12 | Completed | 13500000 |  | 13500000 | 100% |  |  | Information Communication and Technology (General)
SPDO-MST-P-23-00018 | Procurement of Tools for Science, Technology, Engineering, and Mathematics & Agric/Space Technology for 51 No. Schools in the State. | To equip students with hands-on, practical skills and modern technological literacy that foster innovation, critical thinking, and career readiness in critical science and applied industries. | All LGAs | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-01-07 | 30/09/2026 | 12 | Ongoing | 70000000 |  | 65000000 | 92.86% |  |  | Schools’ infrastructure construction and rehabilitation | Schools’ infrastructure construction and rehabilitation
SPDO-MST-P-23-00019 | Procurement ICT Software Facilities for 7 No Institutions and Technical Colleges in the State. | To modernize government operations, enhance service delivery efficiency, and drive digital transformation across public institutions. | All LGAs | Ministry of Science & Technology | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2026-01-07 | 30/09/2026 | 12 | Ongoing | 130000000 |  | 50000000 | 38.46% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-MTR-P-23-00001 | Expansion and upgrade (engineering design, as well as the rehabilitation of the existing runway, the permeter fence and the construction of erosion measure | Increase flight operation, thereby enhancing ease of doing business | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-01-01 | 30/06/2025 | 156 | Ongoing | 35000000000 |  | 6000000000 | 40% |  |  | Airways - General
SPDO-MTR-P-23-00002 | Purchase and Installation of Navigation Aids | Formation of Peace & Reconciliation in Communities in the State | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00003 | Expansion and Upgrading of Taraba State Airport in Jalingo | Expansion and Upgrading of Taraba State Airport in Jalingo | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2000000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00004 | Construction of Terminal Buuilding/Calibration of VOR | Construction of Terminal Buuilding/Calibration of VOR | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 400000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00005 | Implementation of Taraba State Road Traffic and Motorcycle Agency | Implementation of Taraba State Road Traffic and Motorcycle Agency | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 245000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00006 | Provision for Perimeter and Erosion Control | Provision for Perimeter and Erosion Control | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 700000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00007 | Construction of Trailers Park | Construction of Trailers Park | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00008 | Purchase of Flying Board/Life Jacket | Purchase of Flying Board/Life Jacket | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00009 | Design and Construction of Taraba State Driving School | Design and Construction of Taraba State Driving School | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 220000000 |  |  | 0% |  |  | Airways - General
SPDO-MTR-P-23-00010 | Construction of Office Accommodation | Construction of Office Accommodation | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  |  | 0% |  |  | Road General
SPDO-MTR-P-23-00011 | Expension and upgrade (rehabiliation of VIP Toilet | To improve sanitary condition | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-02-10 | 31/03/2024 | 24 | Completed | 10000000 |  | 10000000 | 100% |  |  | Airways - General
SPDO-MTR-P-23-00012 | Expansion and upgrade (Expansion/Extension of the VIP lounge) of the Dan-Baba Suntai Airport, Jalingo | Create conductive environment | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-02-10 | 31/03/2024 | 24 | Completed | 48000000 |  | 48000000 | 100% |  |  | Airways - General
SPDO-MTR-P-23-00013 | Expansion and upgrade (supply, delivery services for the relocation of the automatic wenther observation system (AWOS) and other provision of navigational accessories as well as and rehabilitation) at the Dan-Baba Suntai Airport, Jalingo | Resumption of flight operation at the airport | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-02-10 | 31/03/2024 | 24 | Completed | 1500000000 |  | 1307393245.86 | 100% |  |  | Airways - General
SPDO-MTR-P-23-00014 | Rehabilitation of runway, Drainages and construction of perimeter fence at the Airport Jalingo. | To provide safe landing and take-off of air planes. | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/01/2025 | 104 | Ongoing | 22600000000 |  | 16000000000 | 95% |  |  | Airways-General
SPDO-MTR-P-23-00015 | Installation of instrument landing system at the Airport Jalingo. | To provide guidance to airplanes at bad weather | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-08-01 | 31/10/2024 | 40 | Completed | 800000000 |  | 800000000 | 100% |  |  | Airways-General
SPDO-MTR-P-23-00016 | Purchase and supply of 2nos fire Tenders at the Airport. | To provide extinguishing of fire to Airplanes during any incidents | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-07-01 | 31/08/2024 | 104 | Completed | 1300000000 |  | 1300000000 | 100% |  |  | Airways-General
SPDO-MTR-P-23-00017 | Remolding of terminal building and V.VIP lounge | To provide comfort and for privacy to VVIP and VIPs | Jalingo | Ministry of Transportation Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-12-01 | 20/02/2025 | 54 | Ongoing | 140000000 |  | 112000000 | 95% |  |  | Airways-General
SPDO-MWA-P-23-00001 | Provision of Jalingo Primary Water Supply Scheme | It is designed to increase water source to jalingo township | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-02 | 31/07/2024 | 443 | Ongoing | 36000000000 |  | 3250000000 | 95% | Yes | Generate IGR from sales of water. | Water Resources and Rural Development
SPDO-MWA-P-23-00002 | Maintenance and procurement of pumps, transformers and 750 KV/AVR in Magami Jalingo | Maintenance and procurement of pumps, transformers and 750 KV/AVR in Magami Jalingo | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2025-01-01 | 30/6/2025 | 24 | Completed | 60000000 |  | 60000000 | 100% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00003 | Purchase of 3 Inches Water Pumps for 2024 Irrigation Activities | Purchase of 3 Inches Water Pumps for 2024 Irrigation Activities | All LGAs | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 29000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00004 | P-Wash Matching Ground in Jalingo | P-Wash Matching Ground in Jalingo | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00005 | Upgrading of Ibi, Wukari Water Works | Upgrading of Ibi, Wukari Water Works | Ibi, Wukari | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 453805687 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-MWA-P-23-00006 | Extension of Pipelines & Construction of Concrete Tanks for Water Supply Emergence Communities | Extension of Pipelines & Construction of Concrete Tanks for Water Supply Emergence Communities | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 400000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00007 | Provision of WASH Facilities in some Selected Communities in the State | Provision of WASH Facilities in some Selected Communities in the State | Sardauna, Bali, Jalingo, Takum, K/Lamido, Wukari and Zing | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 80000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00008 | Spring & Stream Development at Tamya | Spring & Stream Development at Tamya | Lau | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00009 | Procurement of New Geo-Physical Equipment for Survey | Procurement of New Geo-Physical Equipment for Survey | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00010 | Rehabilitation of Irrigation Scheme Nukkai and Gindin Dorowa | Rehabilitation of Irrigation Scheme Nukkai and Gindin Dorowa | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00011 | Rehabilitation of Spring Water Schemes at Gwomu, Sakaka, Fikyu, Ndukpe, Mbamnga | Rehabilitation of Spring Water Schemes at Gwomu, Sakaka, Fikyu, Ndukpe | Karim Lamido, Kurmi, Sardauna | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-03-03 | 2024-05-04 | 4 | Ongoing | 50000000 |  | 13000000 | 99% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00012 | Constr.and Equipping of Laboratory for Small Towns Water Supply Agency | Constr.and Equipping of Laboratory for Small Towns Water Supply Agency | All LGAs | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 45000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00013 | Provision of WASH Facilities in some Selected Communities in the State | Provision of WASH Facilities in some Selected Communities in the State | All LGAs | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 64034550 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00014 | Rehabilitation & Expan. of Water Supply Schemes -Fikyu, Bantaje, Serti, Jen & Baissa | Rehabilitation & Expan. of Water Supply Schemes -Fikyu, Bantaje, Serti, Jen & Baissa | Kurmi, Wukari, Sardauna, Karim Lamido | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 70000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00015 | Construction of 1No. Water Quality Control Reference Laboratory with Office | Construction of 1No. Water Quality Control Reference Laboratory with Office | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00016 | Raising/Fortification of Perimeter Fence at the Ministry HQtrs | Raising/Fortification of Perimeter Fence at the Ministry HQtrs | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00017 | Purchase of Hygien and Sanitation Equipment in the State | Purchase of Hygien and Sanitation Equipment in the State | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | CLIMATE CHANGE - General
SPDO-MWA-P-23-00018 | Construction of 1870M Drainage from Karofi Water Works to COA | Construction of 1870M Drainage from Karofi Water Works to COA | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 130000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00019 | Rehabilitation of Lau, Donga, Pantisawa and K/Lamido Water Supply Scheme | Rehabilitation of Lau, Donga, Pantisawa and K/Lamido Water Supply Scheme | Lau, Donga, Yorro, Karim Lamido | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00020 | Drilling & Installation of149No. Handpump Fitted Boreholes in 16 LGAs | Drilling & Installation of149No. Handpump Fitted Boreholes in 16 LGAs | All LGAs | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 155000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00021 | Purchase of 1No. Rigs/Accessories | Purchase of 1No. Rigs/Accessories | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 60500000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00022 | Rehabilitation of Water Supply System in Bali and Gembu | Rehabilitation of Water Supply System in Bali and Gembu | Bali, Sardauna | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 715500000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00023 | Establishment of Water Facilities Database | Establishment of Water Facilities Database | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 15000000 |  | 0 | 0% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00024 | Proposal for 3D Mapping and Modelling of Groundwater Resources including Borehole Rehabilitation Across the 16 LGAs in Taraba State, Nigeria | The Proposal for 3D Mapping and Modelling of Groundwater Resources, including Borehole Rehabilitation Across the 16 LGAs in Taraba State is an initiative aimed at assessing, mapping, and digitally modelling the State’s groundwater resources to improve sustainable water-resource planning and access to potable water. | All LGAs | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2026-01-01 | 31/07/2026 | 20 | Ongoing | 2,026,500,719. 85 |  | 2,000,000,000. 00 | 98% |  |  | Water Resources and Rural Development
SPDO-MWA-P-23-00025 | Reconstruction of 500 Cubic Meter Water Tank and Rehabilitation of In-line Chlorination System at Karofi 1 Well Field | The Reconstruction of the 500 Cubic Meter Water Tank and Rehabilitation of the In-line Chlorination System at Karofi 1 Well Field is a water infrastructure rehabilitation project aimed at restoring and improving the storage and treatment capacity of the well field. | Jalingo | Ministry of Water Management & Aquatic Affairs | Ministry | Ministry |  |  | Healthcare |  | Clean water and Sanitation |  | 2026-01-01 | 31/07/2026 | 20 | Ongoing | 250000000 |  | 150000000 | 88% |  |  | Water Resources and Rural Development
SPDO-MWC-P-23-00001 | Completion of children Amusement park | Children Amusement Park | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 2023-09-01 | 2023-12-01 | 16 | Not Started | 760071139.47 |  | 0 | 0% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00002 | Provision for Support to Widows and Orphans in the State | Provision for Support to Widows and Orphans in the State | Jalingo Local Government Area | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2023-09-01 | 2023-12-01 | 16 | Not Started | 100000000 |  | 0 | 0% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00003 | Completion of Acquisition Centre in the 3 Senatorial Zone | Completion of skills acquisition Centre in Donga, Southern Senatorial Zone | Donga | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2023-09-01 | 2023-12-01 | 16 | Not Started | 242000000 |  | 0 | 0% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00004 | UN Women: Palliatives to the Poor & Vulnerable Women | Palliatives to the Poor & Vulnerable Women | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2023-09-01 | 2023-12-01 | 16 | Not Started | 50000000 |  | 0 | 0% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00005 | Campaign/Women & Children Protection in Emergency | VAC | Jalingo, Taraba state head quarter | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Good Health and well-being |  | 2023-09-01 | 2023-12-01 | 16 | Not Started | 100000000 |  | 0 | 0% |  |  | Improvement to Human Health (General)
SPDO-MWC-P-23-00006 | Nigeria for Women Activities | Nigeria for Women Activities | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Good Health and well-being |  | 2023-09-01 | 30/06/2024 | 52 | Completed | 1151503776.44 |  | 2501127271.62 | 100% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00007 | Advocacy/SDG | Provision for women and children | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Good Health and well-being |  | 2023-09-01 | 2023-12-01 | 16 | Not Started | 60000000 |  | 0 | 0% |  |  | Improvement to Human Health (General)
SPDO-MWC-P-23-00008 | Care & Support for OVC | Care and support of Orphans and Vulnerable | All LGAs | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Good Health and well-being |  | 2023-09-01 | 2023-12-01 | 16 | Ongoing | 100000000 |  | 1985000 | 2% |  |  | Improvement to Human Health (General)
SPDO-MWC-P-23-00009 | Feeding and other needs for 18 trafficked children Protection | Protection | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Healthcare |  | Gender equality |  | 19/1/2024 | 19/1/2024 | 1 | Completed | 5000000 |  | 5000000 | 100% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00010 | Empowerment/exhibition /National celebration | Empowerment exhibition national celebration | Others (Outside the state); | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-01-01 | 2024-09-30 | 36 | Not Started | 50000000 |  | 0 | 0% |  |  | Improvement to Human Health (General)
SPDO-MWC-P-23-00011 | Women fitness/hall fame | For women clinic | Jalingo; | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Healthcare |  | Gender equality |  | 2024-01-01 | 2024-10-01 | 36 | Not Started | 70000000 |  | 0 | 0% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00012 | Children empowerment | Empowering children | All LGAs; | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Economic and Job Creation |  | End Poverty in all its forms |  | 2024-01-01 | 2024-10-02 | 36 | Not Started | 150000000 |  | 0 | 0% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00013 | M&E project, vehicle, office block, stores | Monitoring and evaluation project | Jalingo; | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-10-03 | 36 | Ongoing | 301000000 |  | 69033000 | 30% |  |  | Reform of Government and Governance (General)
SPDO-MWC-P-23-00014 | Children development & national/international celebration | Celebrating national international children | All LGAs; | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Good Health and well-being |  | 2024-01-01 | 2024-10-04 | 36 | Ongoing | 100000000 |  | 10300000 | 2% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00015 | For upkeep of children quarterly release | Protection | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Healthcare |  | Gender equality |  | 2024-01-01 | 31/12/2024 | 52 | Completed | 5000001 |  | 5000001 | 100% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00016 | W/shop at Abuja on ICT and Cyber | Awareness ICT | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Healthcare |  | Gender equality |  | 24/10/2023 | 26/10/2023 | 1 | Completed | 6321750 |  | 6321750 | 100% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00017 | VAAP Campaign/Women & Children Protection in Emergency (GBV)/’] | Protection of Women & Children against Gender Based Violence etc | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Healthcare |  | Gender equality |  | 2024-01-03 | 30/04/2024 | 8 | Completed | 100000000 |  | 100000000 | 100% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00018 | Celebration of Women Day | Celebration of Women Day | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Healthcare |  | Gender equality |  | 2024-08-03 | 2024-08-03 | 1 | Completed | 9700000 |  | 9700000 | 100% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00019 | Release of Tuition Fee to London | Leadership Training | Others (Outside the state); | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 2024-04-12 | 2024-09-12 | 2 | Completed | 11387500 |  | 11387500 | 100% |  |  | Enhancing Skills and Knowledge (General)
SPDO-MWC-P-23-00020 | DTA to Hon. Comm. To attend 6855ng UN | Acceleration of Gender Equality | Others (Outside the state); | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 2024-11-03 | 22/03/2024 | 2 | Completed | 30000000 |  | 30000000 | 100% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00021 | 16 Days Activism | 16 Days Activism | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | NA | NA | 2 | Completed | 11700000 |  | 30000000 | 100% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00022 | Renovation of Shelter home at Tecnobat | Child Protection | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 2023-01-10 | 28/12/2024 | 2 | Ongoing | 300000000 |  | 40800000 | 35% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00023 | International Women’s Day Celebration/Women fitness center & Hall | Celebration of women worldwide, Gender equality | All LGAs | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 2023-01-10 | 28/12/2024 | 2 | Completed | 70000000 |  | 20798500 | 100% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00024 | Advocacy/SDG | Create awareness on GBV | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 2023-01-10 | 28/12/2024 | 60 | Completed | 60000000 |  | 60000000 | 100% |  |  | Societal Re-orientation (General)
SPDO-MWC-P-23-00025 | Her Excellency Office Renovation, Remodeling & Furnishing | Provision of Office Accommodation & Hall | Jalingo | Ministry of Women Affairs and Child Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 2024-01-08 | 30/09/2024 | 8 | Not Started | [6 empty] | Societal Re-orientation (General)
SPDO-MWI-P-23-00001 | Design and construction of Mararraban Baissa-Abong Road (82km) | Design and Construction | Donga;Kurmi; | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2018-09-18 | 2024-12-18 | 211 | On hold | 3500000000 |  | 11558683937.31 | 42% | No |  | Road (General)
SPDO-MWI-P-23-00002 | Dualization of Jallingo City Gates (18km) | Design and Construction | Jalingo; | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2019-12-19 | 2024-12-18 | 260 | Ongoing | 5326456183 |  | 35500720625.15 | 98% | No |  | Road (General)
SPDO-MWI-P-23-00003 | Design and construction of Pamanga-Dakka Road (35km) | Design and Construction | Bali; | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2021-10-02 | 2024-09-03 | 184 | On hold | 5744356980 |  | 8981414277.24 | 45% | Yes | Receipt from the State IGR | Road (General)
SPDO-MWI-P-23-00004 | Construction of Yerima-Gassol-Dominion Farm (24km) Road | Design and Construction | Gassol; | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2021-11-10 | 2024-06-17 | 110 | On hold | 4891281365.75 |  | 3663629277.13 | 44.6% | Yes | Flow of market activities via the route | Road (General)
SPDO-MWI-P-23-00005 | Design and construction of Wukari-Tsukundi-Nddo Iddi Road | Design and Construction of Road | Kurmi; | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2017-06-13 | 2023-12-03 | 319 | Ongoing | 1650787422 |  | 6039248664.67 | 98.7% | No |  | Road (General)
SPDO-MWI-P-23-00006 | Construct and Rehabilitation of Government House Road networks | Construction | Jalingo; | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Security, Peace, and Unity |  | Partnerships for the Goals |  | 2023-01-12 | 2023-06-15 | 54 | On hold | 1000000000 |  | 1500000000 | 30% | No |  | Road (General)
SPDO-MWI-P-23-00007 | Design and construction of Lacheke-Pantisawa Road (18km) | Design and Construction of Road | Yorro; | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2017-08-10 | 2024-06-12 | 366 | Ongoing | 3549191298 |  | 4189644247.41 | 97% | No |  | Road (General)
SPDO-MWI-P-23-00008 | Design and construction of Donga-Mararraba Road with Spur to Suntai | Design and construction of Donga-Mararraba Road with Spur to Suntai | Donga, Bali | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 25000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00009 | Construction of mararraban Kunini-Kunini-Kwantanga Road | Construction of mararraban Kunini-Kunini-Kwantanga Road | Lau | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00010 | Design and construction of Gembu-Bang Road (35KM) | Design and construction of Gembu-Bang Road (35KM) | Sardauna | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00011 | Design and construction of Takum-Lissam Road (2.5km) | Design and construction of Takum-Lissam Road (2.5km) | Takum | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Ongoing | 650000000 |  | 534450916.13 | 100% |  |  | Road - General
SPDO-MWI-P-23-00012 | Design and construction of Trailer Parks | Design and construction of Trailer Parks | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Ongoing | 7,560,939,531.71 |  | 3780469765.86 | 50% |  |  | Road - General
SPDO-MWI-P-23-00013 | Construction of Township Roads in the 3 Senatorial District | Construction of Township Roads in the 3 Senatorial District | All LGAs | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00014 | Construction of Jalingo Township Roads | Construction of Jalingo Township Roads | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00015 | Design and Construction of Jibu Road in Wukari LGA, Gindin-Dorowa (33.6KM) | Design and Construction of Jibu Road in Wukari LGA, Gindin-Dorowa (33.6KM) | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00016 | Design and Construction of Kente-Chinkai Road in Wukari LGA, (19KM | Design and Construction of Kente-Chinkai Road in Wukari LGA, (19KM | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00017 | Design and Construction of Nwukyu-Benkaho Road in Wukari LGA, Gindin-Dorowa (30KM) | Design and Construction of Nwukyu-Benkaho Road in Wukari LGA, Gindin-Dorowa (30KM) | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00018 | Muslim Council-Albaz-Gospel House Road 1.5km, Jalingo | Muslim Council-Albaz-Gospel House Road 1.5km, Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00019 | Angwan Kasa-NNPC-Deeper Life Camp Road 4.5km, Jalingo | Angwan Kasa-NNPC-Deeper Life Camp Road 4.5km, Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00020 | Motor park-Mansur Primary School-Chief Palace Road 2.5km, Gembu. | Motor park-Mansur Primary School-Chief Palace Road 2.5km, Gembu. | Sardauna | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00021 | Old Motor Park-First Baptist Church-Gechan Hospital Road (7km) in Jalingo | Old Motor Park-First Baptist Church-Gechan Hospital Road (7km) in Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00022 | Soyoyo Road (Hospital Ward) Wukari | Soyoyo Road (Hospital Ward) Wukari | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 1000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00023 | Cemetery Road through Lagos Area (Avyi Ward) Wukari | Cemetery Road through Lagos Area (Avyi Ward) Wukari | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00024 | Kinkiso Road by Abiten Motel (Puje Ward) | Kinkiso Road by Abiten Motel (Puje Ward) | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 1000000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00025 | Provision of Mechanical/Electrical Tools | Provision of Mechanical/Electrical Tools | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00026 | Construction of New Government House (Access road) | Stimulate economic activities and enhances security surveillance | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Ongoing | 1700000000 |  | 1500000000 | 53% |  |  | Road - General
SPDO-MWI-P-23-00027 | Construction of Yearly 100 Housing Units Programme | Construction of Yearly 100 Housing Units Programme | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 510000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00028 | Provision for Estates/Quarters in the State | Provision for Estates/Quarters in the State | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 50570000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00029 | Completion of an Office Block and furnishing | Completion of an Office Block and furnishing | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 30735000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00030 | Provision of Services for Housing Developments | Provision of Services for Housing Developments | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 106500000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00031 | Complepletion of 30 units of TSHP II at Zing for COE | Complepletion of 30 units of TSHP II at Zing for COE | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 224056069 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00032 | Construction of A6 Room office Block for Housing Corporation | Construction of A6 Room office Block for Housing Corporation | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 15284447 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00033 | Rehabilitation of Property Rating | Rehabilitation of Property Rating | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 80000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00034 | Completion of Purchased House at Sabon gari Jalingo | Completion of Purchased House at Sabon gari Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00035 | Construction of Military Base at 2 Senatorial Zones (Wukari,Apawa and Mararraba Zing) | Construction of Military Base at 2 Senatorial Zones (Wukari,Apawa and Mararraba Zing) | Wukari, Yorro, Zing | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 2500000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00036 | Design and Construction of Jin-Ndibam - Kuru Jidu community | Design and Construction of Jin-Ndibam - Kuru Jidu community | Ussa | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Road - General
SPDO-MWI-P-23-00037 | Reconstruction of the three cell box culvert at furmi village nguroje constituency,sadauna LGA | Link furmi and nguroje village | Sardauna | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 15/04/2024 | 15 | Completed | 45000000 |  | 45000000 | 100% |  |  | Road - General
SPDO-MWI-P-23-00038 | Remodeling/ renovation of presidential loadge | Renovation and Remodelling of Presidential Lodge, Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 15/04/2024 | 15 | Completed | 1534765553.53 |  | 1,734,763,553.53 | 100% |  |  | Road - General
SPDO-MWI-P-23-00039 | Construction of seven bedroom duplex at old governors lodge wukari | Provided safety accommodation | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 15/04/2024 | 15 | Ongoing | 800000000 |  | 350000000 | 43% |  |  | Road - General
SPDO-MWI-P-23-00040 | Renovation of quarters at DDI garden for air force | Renovation of quarters at DDI garden for air force | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 15/04/2024 | 15 | Completed | 5000000 |  | 5000000 | 100% |  |  | Road - General
SPDO-MWI-P-23-00041 | Additional power light DDI house government loadge wukari | To provide light to government loadge | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-01 | 15/04/2024 | 15 | Ongoing | 22618600 |  | 22618600 | 100% |  |  | Road - General
SPDO-MWI-P-23-00042 | Construction of 22 Km Dual Carriageway from NYSC Camp along Wukari Road to Pantinapu City Gate along Yola road with Pedestrian Walkways, Nukkai Bridge, a Flyover and 6 Nos Pedestrian Bridges in Jalingo, Taraba State. | Stimulate economic activities and enhances security surveillance | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2020-01-01 | 31/12/2024 | 208 | Ongoing | 2,500,000.000.00 |  | 37646239607.69 | 96% |  |  | Road - General
SPDO-MWI-P-23-00043 | Construction and Rehabilitation of Government House road networks | Stimulate economic activities and enhances security surveillance | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-04 | 31/12/2024 | 24 | Ongoing | 1000000000 |  |  | 30% |  |  | Road - General
SPDO-MWI-P-23-00044 | Construction of Ultra-Modern Abattoir | For State Development | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-04 | 31/12/2024 | 24 | Ongoing | 6,084,895,681.60 |  | 4,328,953,958.16 | 71.1% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00045 | Renovation/Construction of State Secretariat | For State Development | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-03-25 | 31/10/2025 | 48 | Ongoing | 1,591,632,882.60 |  | 1591632882.6 | 40% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00046 | Construction of International Trade fair Complex | For State Development | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2023-12-07 | 31/10/2025 | 72 | Ongoing | 8873927392.5 |  | NA |  |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00047 | Renovation of Governor’s Lodge, Wukari | For State Development | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-04 | 31/12/2024 | 24 | Completed | 1481881713.24 |  | 1481881713.24 | 100% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00048 | Construction of International Yam Market, Wukari | For State Development | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2024-01-04 | 31/10/2025 | 48 | Ongoing | 29,125,426,353.06 |  | 3,299,996,717.00 | 11.3% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00049 | Road Construction | Construction of 22km Dual Carriageway from the NYSC Permanent Orientation Camp along Wukari Road to the City Gate at Pantinapu along Yola Road including Pedestrian Walkways, a Bridge Across Nukkai River, a Flyover and 6 No. Pedestrian Bridges in Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Completed | 47387684518.14 |  | 40146239607.69 | 100% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00050 | Road Construction | Construction of Mararaba Pantisawa (Lacheke) – Pantisawa Road | Yorro | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 17206139058.72 |  | 9689644347.99 | 68% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00051 | Road Construction | Construction of Mararraba – Baissa – Abong Road Lot I | Kurmi | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 19141549090.27 |  | 9812830605.79 | 55% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00052 | Road Construction | Construction of Mararraba – Baissa – Abong Road Lot II | Kurmi | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 18700878834.36 |  | 10949570916.52 | 65% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00053 | Road Construction | Construction of Mararraba – Baissa – Abong Road Lot III | Kurmi | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 19592814116.64 |  | 10371768312.74 | 52% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00054 | Road Construction | Construction of Pamanga – Dakka Road | Bali | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 25483763597.92 |  | 15981414277.24 | 65% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00055 | Road Construction | Construction of Yerima – Gassol – Dominion Farm | Gassol | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 16987569432.27 |  | 9163629277.13 | 35% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00056 | Road Construction | Construction of Wukari (Riti) -Kente-Chinkai Road – 35km | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 37428548899.9 |  | 7000000000 | 36% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00057 | Road Construction | Construction of 5km IBI – Nwunyo Road | Ibi | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Completed | 3088400175 |  | 1000000000 | 100% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00058 | Road Construction | Construction of Takum – Lissam (12km) | Takum | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 11743514265 |  | 3000000000 | 15% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00059 | Road Construction | Construction of Jalingo Township Roads | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 21681706403.67 |  | 5300000000 | 24% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00060 | Road Construction | Construction of Wukari Township Road Network and the Takum Junction Flyover Bridge with Dual Carriageway Interchange | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 85904853390.22 |  | 5000000000 | 10% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00061 | Road Construction | Construction of Zing – Yakoko – Mookin – Lamina Road | Zing | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 34918166780.96 |  | 1500000000 | 5% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00062 | Remodelling and Constructions | Renovation, remodelling and Rehabilitation of Taraba State Liaison Office, Abuja | Others (Outside the state); | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 4612858075.79 |  | 1000000000 | 75% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00063 | Remodelling and Constructions | Renovation/Remodelling of T.Y. Danjuma House, Asokoro, Abuja | Others (Outside the state); | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Completed | 1481050534.44 |  | 1481050534.44 | 100% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00064 | Remodelling and Constructions | Renovation/Remodelling of T.Y. Danjuma House, Wukari | Wukari | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Completed | 1078060110.48 |  | 1078060110.48 | 100% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00065 | Remodelling and Constructions | Construction/Furnishing of 1170 Person One-Medium Living Bungalow Block at Government House, Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 8310360110.48 |  | 7519512195.12 | 95% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00066 | Remodelling and Constructions | Construction of Taraba State Data Capturing Centre (TADCC), Central wire House and Canteen Government House, Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 5037391555.5 |  | 1000000000 | 70% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00067 | Remodelling and Constructions | Construction of Government House Chapel, Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 5275478817.39 |  | 5275478817.39 | 80% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00068 | Remodelling and Constructions | Construction of Governor's Office Extension, Combine Security Squad Centre and Fire Service Station | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 3639349452.36 |  | 3500000000 | 95% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00069 | Remodelling and Constructions | Construction of Office of First Lady | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 2949687772 |  | 2949687772 | 60% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00070 | Remodelling and Constructions | Renovation, Rehabilitation and Remodeling of General Sani Abacha State Secretariat, Jalingo | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 1591632882.6 |  | 1591632882.6 | 70% |  |  | Construction/Provision of Roads
SPDO-MWI-P-23-00071 | Procurement and Purchase | Procure 7 No. Fairly used machines and equipments | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Completed | 829686948.56 |  | 829686948.56 | 100% |  |  | Furnishing
SPDO-MWI-P-23-00072 | Procurement and Purchase | Development of Taraba Oasis Project (Algon House) | Jalingo | Ministry of Works & Infrastructure Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Sustainable cities & Communities |  | 2026-01-01 | 30/07/2026 | 52 | Ongoing | 14624446369.8 |  | 360000000 | 2.462% |  |  | Construction/Provision of Roads
SPDO-MWM-P-23-00001 | Purchase of 500No. Pieces of Industrial Waste Bin Clargy | Purchase Of Waste Bin Containers | All LGAs; | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Clean water and Sanitation |  | 2024-04-30 | 2025-10-30 | 72 | Not Started | 35000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MWM-P-23-00002 | Acquisition Of Dumpling Site | Acquisition Of Land For Dumping Of Waste Bin In All The 16 Lgas | All LGAs; | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Healthcare |  | Good Health and well-being |  | 2024-04-30 | 2026-09-30 | 116 | Not Started | 160000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MWM-P-23-00003 | Uniform For Sanitation Workers | Purchase Of Uniform For All The 10,000 Sanitation Workers Across The 16 Local Government Area | All LGAs; | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Decent Work and Economic Growth |  | 2024-04-30 | 2026-09-30 | 116 | Not Started | 400000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MWM-P-23-00004 | Research & Development in the Field of Waste Management | Research And Development For The Ministry | All LGAs; | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Education |  | Quality Education |  | 2024-04-30 | 2026-09-30 | 116 | Not Started | 60000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MWM-P-23-00005 | Provision of Office Equipment | Purchases Of Office Equipment To Facilitate Office Work | Jalingo; | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-04-30 | 2026-09-30 | 116 | Not Started | 100000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MWM-P-23-00006 | Construction of Office Accomodation at Jalingo | Office For The Staff Of The Ministry Since It'S A New Ministry | Jalingo; | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-04-30 | 2026-09-30 | 116 | Not Started | 200000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MWM-P-23-00007 | Purchase of 50No. Community Waste Bin to some Selected Communities in the State | Equipment For Any Workshop Activities. | Jalingo; | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Education |  | Decent Work and Economic Growth |  | 2024-04-30 | 2026-09-30 | 116 | Not Started | 5000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MWM-P-23-00008 | Purchase of 80No. of 1000Litres of Household Waste Bin | Purchase of 80No. of 1000Litres of Household Waste Bin | Jalingo | Ministry of Waste Management and Innovation | Ministry | Ministry |  |  | Economic and Job Creation |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 45000000 |  | 0 | 0% | No |  | Environmental Improvement - General
SPDO-MYS-P-23-00001 | Private Security at Jolly Nyame Stadium | Renovation | Jalingo | Ministry of Youth & Sports Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2023-12-01 | 2027-12-01 | 208 | Not Started | 30000000 |  | 0 | 0% | Yes | Bursting the sport activities within the state and encourage participation even outside the state | Youth - General | No | Not an initiative
SPDO-MYS-P-23-00002 | Job Creation for Unemployed Youths in the State | Youth Empowerment | Jalingo | Ministry of Youth & Sports Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2023-11-30 | 2024-11-30 | 52 | Not Started | 98600000 |  | 0 | 0% | No |  | Poverty Alleviation - General
SPDO-MYS-P-23-00003 | Youth Behavioural Change | Youth Empowerment | All LGAs | Ministry of Youth & Sports Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Good Health and well-being |  | 2024-04-15 | 2024-04-15 | 52 | Not Started | 109143410 |  | 0 | 0% | No |  | Youth - General
SPDO-MYS-P-23-00004 | Sports Development Programme | Youth Empowerment | Jalingo | Ministry of Youth & Sports Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | End Poverty in all its forms |  | 2024-03-04 | 2025-03-04 | 52 | Not Started | 1843914304 |  | 0 | 0% | No |  | Youth - General
SPDO-MYS-P-23-00005 | FC Taraba Sporting Activities | Youth Empowerment | Jalingo | Ministry of Youth & Sports Development | Ministry | Ministry |  |  | Women and Youth Empowerment |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 166223333 |  | 0 | 0% |  |  | Youth - General
SPDO-MYS-P-23-00006 | Renovation of Sembe Lodge | Youth Empowerment | Jalingo | Ministry of Youth & Sports Development | Ministry | Ministry |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 31/12/2024 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Youth - General
SPDO-NEP-P-23-00001 | Baseline Survey & Poverty Mapping | Baseline Survey & Poverty Mapping | Jalingo | NEPAD Taraba Coordinating Unit | Department | Office of the Governor |  |  | Women and Youth Empowerment |  | No Poverty |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4070773 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-NEP-P-23-00002 | Provision for Women in Aquaculture Programme in the State | Provision for Women in Aquaculture Programme in the State | Jalingo | NEPAD Taraba Coordinating Unit | Department | Office of the Governor |  |  | Women and Youth Empowerment |  | Reduced Inequality |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1400000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-NEP-P-23-00003 | Office Development/Construction | Office Development/Construction | Jalingo | NEPAD Taraba Coordinating Unit | Department | Office of the Governor |  |  | Women and Youth Empowerment |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3500000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-NEP-P-23-00004 | Gender & Climate Change SMART Agriculture | Gender & Climate Change SMART Agriculture | Jalingo | NEPAD Taraba Coordinating Unit | Department | Office of the Governor |  |  | Women and Youth Empowerment |  | Gender equality |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4900000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-NEP-P-23-00005 | Establishment of NEPAD Youth Clubs in Secondary Schools | Establishment of NEPAD Youth Clubs in Secondary Schools | Jalingo | NEPAD Taraba Coordinating Unit | Department | Office of the Governor |  |  | Women and Youth Empowerment |  | Economic and Job Creation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4340000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-NEP-P-23-00006 | Provision of ICT for Youth Initiative | Provision of ICT for Youth Initiative | Jalingo | NEPAD Taraba Coordinating Unit | Department | Office of the Governor |  |  | Women and Youth Empowerment |  | Economic and Job Creation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4200000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-NEP-P-23-00007 | NEPAD Resource Centre in Jalingo | NEPAD Resource Centre in Jalingo | Jalingo | NEPAD Taraba Coordinating Unit | Department | Office of the Governor |  |  | Women and Youth Empowerment |  | Economic and Job Creation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1400000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OAS-P-23-00004 | Inspection and Evaluation of Government Projects | Inspection and Evaluation of Government Projects | All LGAs | Office of the Auditor General (State) | Office | Office of the Auditor General |  |  | Women and Youth Empowerment |  | Economic and Job Creation |  | 15/1/2023 | 31/12/2024 | 104 | Not Started | 10000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-ODG-P-23-00001 | Renovation and Furnishing of Office & Guest House of the Deputy Governor | Renovation and Furnishing of Office & Guest House of the Deputy Governor | Jalingo | Office of the Deputy Governor | Office | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 885000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OEG-P-23-00001 | Renovation of Government House Jalingo and Government Lodges | Renovation of Government House Jalingo and Government Lodges | Jalingo | Office of the Executive Governor | Office | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OEG-P-23-00002 | Renovation of Government House Facilities | Renovation & Remodelling main Building, 4 main Guest Houses, Kitchen, External Jim laundry, In-door Swimming pool, & Changing room. 1No. & Scrapping Solar (30KVA) Light, Car park, Water supply | Jalingo | Office of the Executive Governor | Office | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-08-09 | 31/12/2024 | 104 | Ongoing | 2897811945.5 |  | 2897811945.5 | 85% |  |  | Reform of Government and Governance - General
SPDO-OEG-P-23-00003 | Furnishing, Remodelling and Renovation of Guest House | Furnishing, renovation & remodeling of gate, guest house, kitchen, landscaping & perimeter fencing, electrical/electronics, gazebo, water purification | Jalingo | Office of the Executive Governor | Office | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2023-08-09 | 31/12/2024 | 104 | Ongoing | 5100545991.95 |  | 3000000000 | 75% |  |  | Reform of Government and Governance - General
SPDO-OEG-P-23-00004 | Renovation of Governor's Office Security Architecture | Governor’s office, security lounge warehouse, landscaping, underground piping, 3 Nos boreholes, CSO office Upgrade , New office blocks by Gate 1, Glass tunnel, 40KVA solar light, swimming pool, acrylic glass Doom with Furniture & Air Condition | Jalingo | Office of the Executive Governor | Office | Office of the Governor |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-07-01 | 31/07/2025 | 52 | Ongoing | 10450349656.66 |  | 10450349656.66 | 80% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00001 | Purchase of Fixed Assets/Materials General | Purchase of Senator Anthony Manzo residence, Zing | Zing | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-03-25 | 2024-12-31 | 52 | Ongoing | 264383000 |  | 154000000 | 58.25% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00002 | Renovation & Furnishing of State Liaison Offices | Renovation & Furnishing of State Liaison Offices | Others (Outside the state); | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00003 | Coordination and implementation of UNICEF activities | Coordination and implementation of UNICEF activities | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 153203424 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00004 | Capital Subvention to Yangtu Special Development Area. | Capital Subvention to Yangtu Special Development Area. | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 120000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00005 | Capital Subvention to NGADA Special Development Area. | Capital Subvention to NGADA Special Development Area. | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 120000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00006 | Purchase of 100No. Computers to be Distributed to all the MDAs in the State | Purchase of 100No. Computers to be Distributed to all the MDAs in the State | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 80000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00007 | Construction of New Governors Lodge in Gembu | Remodelling & Construction of Alli at Government Lodge Gembu | Sardauna | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00008 | Construction of New Governors Lodge in Kakara | Construction of Government Lodge, Kakara | Sardauna | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 2370302169.1 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00009 | Upgrading and Construction of Additional Structures in the Government Guest House Wukari | Upgrading and Construction of Additional Structures in the Government Guest House Wukari | Wukari | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00010 | Construction of One Store Building for Government Lodge Takum | Remodeling & construction of additional structure at Government Lodge, Takum | Takum | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 341580148.77 |  | 202198468.62 | 59.2% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00011 | Renovation and Fencing of Government Lodge 77 in Yola | Renovation and Fencing of Government Lodge 77 in Yola | Yola | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00012 | Construction and Renovation of Government Guest House Bali | Remodelling and Reconstructution of Additional Structure at Government House, Bali | Bali | Office of the SGS - General Services | Office | Office of the SGS |  |  | Women and Youth Empowerment |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4300438628.76 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00013 | Purchase of Residential Buildings to be Converted as Government Guest Houses | Purchase of Abubakar Barde House, Jalingo | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 548780487.8 |  | 100000000 | 18.22% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00014 | Purchase of 20No. Furniture and Fittings at Secretary to the State Government Office | Purchase of 20No. Furniture and Fittings at Secretary to the State Government Office | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00015 | Provision of Additional Government Houses as Residential Building for Federal Agencies Staff | Provision of Additional Government Houses as Residential Building for Federal Agencies Staff | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 80000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00016 | Renovation of Wukari and Gembu Government Lodges | Renovation of Wukari and Gembu Government Lodges | Wukari, Sardauna | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 250000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00017 | Purchase of Building to expand Government Buiilding | Purchase of twin building opposite Presidential Lodge, Jalingo | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 378000000 |  | 160400000 | 42.43% |  |  | Reform of Government and Governance - General
SPDO-OSG-P-23-00018 | Request for Payment of outstanding judgement debt | Request for Payment of outstanding judgement debt | Jalingo | Office of the SGS - General Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 30000000 |  | 17508000 | 58.36% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00001 | Procurement of Foam Chemical Compound/Fire fighting tool | Procurement of Foam Chemical Compound/Fire fighting tool | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 65000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00002 | Servicing & Installation of Fire Extinguishers | Servicing & Installation of Fire Extinguishers | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 40000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00003 | Procurement of Uniforms & Accessories for 150 Personnel | Procurement of Uniforms & Accessories for 150 Personnel | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 8890000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00004 | Purchase of 2No. Fire Fighting Engines | Purchase of 2No. Fire Fighting Engines | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 94000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00005 | Purchase of Marshal's Kitting | Purchase of Marshal's Kitting | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 350000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00006 | Provision for Intellegience Gathering and Sharing | Provision for Intellegience Gathering and Sharing | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00007 | Engagement of Air Force/Air Surveillance | Engagement of Air Force/Air Surveillance | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00008 | Support to Taraba Security Outfit (Marshall) | Support to Taraba Security Outfit (Marshall) | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2181613362 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00009 | Equipping & Support to Federal Troops | Equipping & Support to Federal Troops | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2000000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00010 | Procurement of 36No. Surveillance Drones | Procurement of 36No. Surveillance Drones | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 300000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00011 | Radio System | Radio System | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00012 | Logistics for Clearance Operations | Logistics for Clearance Operations | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00013 | Early Warning, Early Response (EWERs) | Early Warning, Early Response (EWERs) | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1200000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00014 | Procurment of Essential Security Equipment: Ballistic Helmets and Bullet Proof Vests for Taraba State Police | Procurment of Essential Security Equipment: Ballistic Helmets and Bullet Proof Vests for Taraba State Police | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 4956000000 |  | 3300000000 | 66.59% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00015 | Purchase for Security Equipmenrt as State Support to Security Agencies in the State | Purchase for Security Equipmenrt as State Support to Security Agencies in the State | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Ongoing | 7315460750 |  | 3000000000 | 41.01% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00016 | Procurement of 6 Channel Vehicles Catcher System | Procurement of 6 Channel Vehicles Catcher System | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2025-01-01 | 2025-12-31 | 52 | Ongoing | 1128750000 |  | 1278750000 | 113.3% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00017 | Procurement of Four (4) Mine Resistant Ambush Protected (MRAP) Vehicles | Procurement of Four (4) Mine Resistant Ambush Protected (MRAP) Vehicles | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2025-01-01 | 2025-12-31 | 52 | Ongoing | 3109993500 |  | 1117318435.76 | 35.93% |  |  | Reform of Government and Governance - General
SPDO-OSH-P-23-00018 | Procurement of 10 Armored Military Buffalo Vehicles | Procurement of 10 Armored Military Buffalo Vehicles | Jalingo | Office of the SGS - Home Affairs & Special Services | Office | Office of the SGS |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2025-01-01 | 2025-12-31 | 52 | Ongoing | 2759793750 |  | 1000000000 | 36.23% |  |  | Reform of Government and Governance - General
SPDO-PHC-P-23-00001 | Construction of Taraba State PHCDA Permanent Site | Construction of Taraba State PHCDA Permanent Site | Jalingo | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 415453500 |  | 0 | 0% |  |  | Functional health facilities
SPDO-PHC-P-23-00002 | Utilisation of Essential Package of Health Care Services | Utilisation of Essential Package of Health Care Services | Jalingo | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 15940000 |  | 0 | 0% |  |  | Emergency services
SPDO-PHC-P-23-00003 | Purchase of Furniture and Office Equipment | Purchase of Furniture and Office Equipment | Jalingo | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10900000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-PHC-P-23-00004 | Coordination of Nutrition Activities | Coordination of Nutrition Activities | Jalingo | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 187000000 |  | 0 | 0% |  |  | Health sector coordination mechanisms
SPDO-PHC-P-23-00005 | Coordination of Basic Health Care Provision Fund | Coordination of Basic Health Care Provision Fund | Jalingo | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 120000000 |  | 0 | 0% |  |  | Health sector coordination mechanisms
SPDO-PHC-P-23-00006 | Coordination Funding for GAVI Activities in the State | Coordination Funding for GAVI Activities in the State | Jalingo | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Women and Youth Empowerment |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Health sector coordination mechanisms
SPDO-PHC-P-23-00007 | Coordination of UNICEF Activities in the State | Coordination of UNICEF Activities in the State | Jalingo | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Health sector coordination mechanisms
SPDO-PHC-P-23-00008 | Upgrading of Health Facilities 48No. across the State | Upgrading of Health Facilities 48No. across the State | All LGA's | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 636438484 |  | 0 | 0% |  |  | Functional health facilities
SPDO-PHC-P-23-00009 | Construction of Model Primary Health Care Centre Level 2 (Lau PHCC) | Construction of Model Primary Health Care Centre Level 2 (Lau PHCC) | Lau | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 55000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-PHC-P-23-00010 | Construction of Model Primary Health Care Centre Level 2 (Ndaforo PHCC) | Construction of Model Primary Health Care Centre Level 2 (Ndaforo PHCC) | Sardauna | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 55000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-RWA-P-23-00001 | Coordinatioon of State Inclusive Basic Service Delivery, Livelihood & Empowerment Integrated Programme | Coordinatioon of State Inclusive Basic Service Delivery, Livelihood & Empowerment Integrated Programme | Jalingo | Rural Water Supply & Sanitation Agency | Agency | Ministry of Water Management and Aquatic Affairs |  |  | Security, Peace, and Unity |  | Sustainable cities & Communities |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 9955935.52 |  | 0 | 0% |  |  | Water Resources and Rural Deve - General
SPDO-RWA-P-23-00002 | Purchase of Water, Sanitation and Hygien Equipment in the State | Purchase of Water, Sanitation and Hygien Equipment in the State | Jalingo | Rural Water Supply & Sanitation Agency | Agency | Ministry of Water Management and Aquatic Affairs |  |  | Security, Peace, and Unity |  | Clean water and Sanitation |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5486808.49 |  | 0 | 0% |  |  | Water Resources and Rural Deve - General
SPDO-RWA-P-23-00003 | Coordination of Livelihoodand Empowerment Activities at the State Level | Coordination of Livelihoodand Empowerment Activities at the State Level | Jalingo | Rural Water Supply & Sanitation Agency | Agency | Ministry of Water Management and Aquatic Affairs |  |  | Women and Youth Empowerment |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 397722547 |  | 0 | 0% |  |  | Water Resources and Rural Deve - General
SPDO-SIE-P-23-00002 | Construction of Office Secretariat, Jalingo | Construction of Office Secretariat, Jalingo | Jalingo | State Independent Electoral Commission (SIEC) | Agency | INEC Office |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-SIE-P-23-00003 | Establishment of Database at the HQ Office | Establishment of Database at the HQ Office | Jalingo | State Independent Electoral Commission (SIEC) | Agency | INEC Office |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-SMA-P-23-00001 | Provision for Emergency and Disaster Occurrence and Relief Materials | Provision for Emergency and Disaster Occurrence and Relief Materials | Jalingo | State Emergency Management Agency | Agency | Office of the Governor |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-SME-P-23-00001 | General Entrepreneurship Development (Capacity Training) | General Entrepreneurship Development (Capacity Training) | All LGAs | Agency for Small & Medium Scale Enterprises | Agency | Ministry of Commerce Trade and Industry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 107000000 |  | 0 | 0% |  |  | Growing the Private Sector - General
SPDO-SME-P-23-00002 | Baseline Economic Survey on Micro, Small & Medium Enterprises | Baseline Economic Survey on Micro, Small & Medium Enterprises | All LGAs | Agency for Small & Medium Scale Enterprises | Agency | Ministry of Commerce Trade and Industry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Growing the Private Sector - General
SPDO-SME-P-23-00003 | Small Scale Industries Credit Schemes | Small Scale Industries Credit Schemes | All LGAs | Agency for Small & Medium Scale Enterprises | Agency | Ministry of Commerce Trade and Industry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 37792881 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-SME-P-23-00004 | Taraba MSMEs Expo (Exhibition) | Taraba MSMEs Expo (Exhibition) | All LGAs | Agency for Small & Medium Scale Enterprises | Agency | Ministry of Commerce Trade and Industry |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 21000000 |  | 0 | 0% |  |  | Growing the Private Sector - General
SPDO-SSA-P-23-00001 | 300 sanitation jobs: | Created for women and youths in Jalingo within 74 hours of assumption and is a continues process | All LGAs | State Sanitation Agency | Agency | Ministry |  |  | Women and Youth Empowerment |  | Gender equality |  | 30/05/2023 | 2023-01-06 | 4 | Ongoing | 175500000 |  | 175500000 | 100% |  |  | Societal Re-orientation (General)
SPDO-TAD-P-23-00001 | Agricultural Extension Services in the State | Agricultural Extension Services in the State | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 21070000 |  | 0 | 0% |  |  | Animal health and livestock diseases management
SPDO-TAD-P-23-00002 | Renovation of Farm Training Centre | Renovation of Farm Training Centre | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3920000 |  | 0 | 0% |  |  | Capacity building for stakeholders and professional human resources development
SPDO-TAD-P-23-00003 | Agric - Technical Services | Agric - Technical Services | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 6860000 |  | 0 | 0% |  |  | Livestock feeds development
SPDO-TAD-P-23-00004 | Purchase of Vinach, Glyspreng and 24D Amine for Control of Herbicides in the State | Purchase of Vinach, Glyspreng and 24D Amine for Control of Herbicides in the State | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Life On Land |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 14700000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-TAD-P-23-00005 | Planning, Monitoring & Evaluation Activities | Planning, Monitoring & Evaluation Activities | All LGA's | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 7350000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-TAD-P-23-00006 | Procurement of Animal Drawn Plows & Ridges | Procurement of Animal Drawn Plows & Ridges | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2450000 |  | 0 | 0% |  |  | Animal health and livestock diseases management
SPDO-TAD-P-23-00007 | Procurement of Irrigation Pumps | Procurement of Irrigation Pumps | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 24900000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-TAD-P-23-00008 | Procurement of Office Furniture | Procurement of Office Furniture | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 24500000 |  | 0 | 0% |  |  | Agriculture Programme Not Elsewhere Classified
SPDO-TAD-P-23-00009 | Electrification of Office Building | Electrification of Office Building | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2450000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-TAD-P-23-00010 | Purchase of Work Bulls | Purchase of Work Bulls | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2450000 |  | 0 | 0% |  |  | Intensive crop and vegetable production (irrigation, crop diversification etc.)
SPDO-TAD-P-23-00011 | Procurement of Tubewells & Washbores Equipment | Procurement of Tubewells & Washbores Equipment | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 12450000 |  | 0 | 0% |  |  | Integrated rural development (agricultural land development, farm mechanization, & rural infrastructures
SPDO-TAD-P-23-00012 | Compensation of Farm Training Centre Land | Compensation of Farm Training Centre Land | Jalingo | Taraba Agricultural Devt. Project (TADP) | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4900000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-TAP-P-23-00001 | Purchase of Grains/Cash Crops Assorted | Purchase of Grains/Cash Crops Assorted | Jalingo | Taraba Agricultural Produce Marketing Agency | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Zero Hunger |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 408900000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TAP-P-23-00002 | Rehabilitation of kurmi Storage Facility, Gassol. | Rehabilitation of kurmi Storage Facility, Gassol. | Kurmi | Taraba Agricultural Produce Marketing Agency | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TAP-P-23-00003 | Renovation of Warehouses Karim, Takum and Wukari | Renovation of Warehouses Karim, Takum and Wukari | Karim Lamido, Takum, Wukari | Taraba Agricultural Produce Marketing Agency | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TAP-P-23-00004 | Construction of 3No. Warehouse at Jalingo, Wukari and Gashaka | Construction of 3No. Warehouse at Jalingo, Wukari and Gashaka | Jalingo, Wukari, Gashaka | Taraba Agricultural Produce Marketing Agency | Agency | Ministry of Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TCA-P-23-00001 | Provision for the Implementation of HIV/AIDS Activities and Outreach Programme in Taraba State | Provision for the Implementation of HIV/AIDS Activities and Outreach Programme in Taraba State | Jalingo | Taraba State Aids Control Agency | Agency | Office of the Governor |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Emergency services
SPDO-TCM-P-23-00001 | Production of 50,000No. Security PT-Code Stickers | Production of 50,000No. Security PT-Code Stickers | Jalingo | Taraba Commercial Motorcycle & Monitoring Agency | Agency | Ministry of Transport and Development |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 8898790 |  | 0 | 0% |  |  | Road - General
SPDO-TCM-P-23-00002 | Production of 50,000No. Customized Reflective Jackets | Production of 50,000No. Customized Reflective Jackets | Jalingo | Taraba Commercial Motorcycle & Monitoring Agency | Agency | Ministry of Transport and Development |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 9101210 |  | 0 | 0% |  |  | Road - General
SPDO-TCM-P-23-00003 | Purchase of 20No. Tricycles | Purchase of 20No. Tricycles | Jalingo | Taraba Commercial Motorcycle & Monitoring Agency | Agency | Ministry of Transport and Development |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 2000000 |  | 0 | 0% |  |  | Road - General
SPDO-TDP-P-23-00001 | Purchase of Drugs & Medical Equipment/Consumables | Purchase of Drugs & Medical Equipment/Consumables | Jalingo | Taraba State Essential Drugs Programme | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 24950100 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TDP-P-23-00002 | Renovation of Central Medical Store/Office Complex | Renovation of Central Medical Store/Office Complex | Jalingo | Taraba State Essential Drugs Programme | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-TSU-P-23-00017 | Renovation of Hostels at the State University, Jalingo | Renovation of Hostels at the State University, Jalingo | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 500000000 |  | 500000000 | 100% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-THU-P-23-00001 | Repair of Tractors | Repair of Tractors | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 26000000 |  | 0 | 0% |  |  | Integrated rural development (agricultural land development, farm mechanization, & rural infrastructures
SPDO-THU-P-23-00002 | Purchase of Disc Plough | Purchase of Disc Plough | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 40000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00003 | Purchase of Disc Harrow | Purchase of Disc Harrow | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 40000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00004 | Renovation of Central Workshop at Jalingo | Renovation of Central Workshop at Jalingo | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-THU-P-23-00005 | Reconstruction of 2No. Workshops at Bali/Wukari | Reconstruction of 2No. Workshops at Bali/Wukari | Bali, Wukari | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 44000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00006 | Renovation of Office Blocks | Renovation of Office Blocks | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00007 | Purchase of 1No. Tool Box (Heavy Duty) | Purchase of 1No. Tool Box (Heavy Duty) | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00008 | Complete Engine Spare Parts | Complete Engine Spare Parts | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00009 | Implement Spare Parts | Implement Spare Parts | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00010 | Purchase of Workshop Tools & Equipment | Purchase of Workshop Tools & Equipment | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 13000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00011 | Purchase of Equipped Mobile Workshops (3No) | Purchase of Equipped Mobile Workshops (3No) | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 3144160 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00012 | Purchase of Vehicles for Monitoring Activites | Purchase of Vehicles for Monitoring Activites | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 32000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00013 | Repair of Crane Lorry | Repair of Crane Lorry | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00014 | Repair of 2No. Combine Harvester | Repair of 2No. Combine Harvester | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 4000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00015 | Construction of 4No. Area & 2 Development Area Offices | Construction of 4No. Area & 2 Development Area Offices | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 42503789 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-THU-P-23-00016 | Purchase of ICT Equipment for Office Use at THU Office | Purchase of ICT Equipment for Office Use at THU Office | Jalingo | Tractor Hiring Unit (THU) | Agency | Ministry Agriculture and Food Security |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1000000 |  | 0 | 0% |  |  | Farm inputs supply and service delivery system (improved seeds, fertilizer, agro-chemicals etc.)
SPDO-TME-P-23-00002 | Mobile Education Programme in the State | Mobile Education Programme in the State | Jalingo | Taraba State Mass Education Board | Agency | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 800000 |  | 0 | 0% |  |  | Early Childhood Care, Development and Education (ECCDE)
SPDO-TME-P-23-00004 | Each One Teach one Educational Programme in the State | Each One Teach one Educational Programme in the State | Jalingo | Taraba State Mass Education Board | Agency | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5000000 |  | 0 | 0% |  |  | Advocacy and sensitization
SPDO-TPS-P-23-00001 | Physical Infrastructure/Programme Upgrade (TETFund) | Physical Infrastructure/Programme Upgrade (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1457321711 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TPS-P-23-00002 | Const./Provision of Classrooms & Hostels (TETFund) | Const./Provision of Classrooms & Hostels (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 350000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TPS-P-23-00003 | Accreditation of Courses | Accreditation of Courses | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 200000000 |  | 0 | 0% |  |  | Tertiary institutions’ new courses accreditation
SPDO-TPS-P-23-00004 | Library Development (TETFund) | Library Development (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TPS-P-23-00005 | Provision of Research and Development Programe (TETFund) | Provision of Research and Development Programe (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Research and development
SPDO-TPS-P-23-00006 | Academic Staff Training General (TETFund) | Academic Staff Training General (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Tertiary institutions’ new courses accreditation
SPDO-TPS-P-23-00007 | Construction and Infrastructure of TETFund Projects and Monitoring (TETFund) | Construction and Infrastructure of TETFund Projects and Monitoring (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Integrated supportive supervision
SPDO-TPS-P-23-00008 | Equipment Fabrications (TETFund) | Equipment Fabrications (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Libraries and laboratories
SPDO-TPS-P-23-00009 | Purchase of ICT Support Equipment (TETFund) | Purchase of ICT Support Equipment (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 8000000 |  | 0 | 0% |  |  | ICT equipment, software and expertise
SPDO-TPS-P-23-00010 | Publication of Journals (TETFund) | Publication of Journals (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 6000000 |  | 0 | 0% |  |  | Research and development
SPDO-TPS-P-23-00011 | Manuscript Development (TETFund) | Manuscript Development (TETFund) | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 6000000 |  | 0 | 0% |  |  | Research and development
SPDO-TPS-P-23-00012 | Purchase of Furniture and Equipment | Purchase of Furniture and Equipment | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Furnishing
SPDO-TPS-P-23-00013 | Provision for Conference Attendance | Provision for Conference Attendance | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Legal, policy, regulations and standards, guidelines and protocols development and reviews
SPDO-TPS-P-23-00014 | Sabatical Leave Grants | Sabatical Leave Grants | Bali | Taraba State Polytechnic, Suntai | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Education Not Elsewhere Classified
SPDO-TSA-P-23-00001 | Construction & Furnishing of 1No. Office Accommodation | Construction & Furnishing of 1No. Office Accommodation | Jalingo | Taraba State Contributory Health Insurance Agency | Agency | Ministry of Health |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 275000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-TSA-P-23-00002 | Capitation for Poor & Vulnerable in the State | Capitation for Poor & Vulnerable in the State | Jalingo | Taraba State Contributory Health Insurance Agency | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 531381101 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-TSA-P-23-00004 | Upgrading of Health Care Facility | Upgrading of Health Care Facility | Jalingo | Taraba State House of Assembly | Agency | State House of Assembly |  |  | Security, Peace and Unity |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 110516750 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-TSA-P-23-00010 | CPA/Parliamentary Tours | CPA/Parliamentary Tours | Jalingo | Taraba State House of Assembly | Agency | State House of Assembly |  |  | Security, Peace and Unity |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1478584608 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-TSA-P-23-00011 | Construction of Model Primary Health Care Centre Level 2 (Byegya PHCC) | Construction of Model Primary Health Care Centre Level 2 (Byegya PHCC) | All LGAs | Primary Health Care Development Agency, Jalingo | Agency | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 104500000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-TSB-P-23-00001 | Boundary Demarcation for Taraba/Benue/Nassarawa/Plateau Project | Boundary Demarcation for Taraba/Benue/Nassarawa/Plateau Project | Jalingo | Taraba State Boundary Commission | Agency | Office of the Governor |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 55000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-TSC-P-23-00001 | Purchase of Cultural Centre | Purchase of Cultural Centre | Jalingo | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSC-P-23-00002 | National Art Festival Activities in the State | National Art Festival Activities in the State | Jalingo | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 25000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSC-P-23-00003 | Taraba Festival Programme | Taraba Festival Programme | Jalingo | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 35000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSC-P-23-00004 | Provision for Craft Expo Programme | Provision for Craft Expo Programme | Jalingo | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 25000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSC-P-23-00005 | Provision for Abuja Carnival Programme | Provision for Abuja Carnival Programme | Abuja | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSC-P-23-00006 | Cultural Exchange Programme | Cultural Exchange Programme | Jalingo | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institution |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 9807826.34 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSC-P-23-00007 | Arewa Festival Programme | Arewa Festival Programme | Jalingo | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institution |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSC-P-23-00008 | Provision for Children Programme in the State | Provision for Children Programme in the State | Jalingo | Taraba State Arts Council | Agency | Ministry of Heritage and Eco-tourism |  |  | Security, Peace, and Unity |  | Peace, Justice and Strong Institutions |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 10000000 |  | 0 | 0% |  |  | Societal Re-orientation - General
SPDO-TSI-P-23-00006 | Provision for Furnishing of TRIRS Headquarters Office, Jalingo | Provision for Furnishing of TRIRS Headquarters Office, Jalingo | Jalingo | Taraba State Internal Revenue Service | Agency | Ministry of Finace, Budget and Economic Planning |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 50000000 |  | 0 | 0% |  |  | Reform of Government and Governance - General
SPDO-TSJ-P-23-00001 | Provision of High Tech and Modern Medical Equipment at Specialist Hospital, Jalingo | Provision of High Tech and Modern Medical Equipment at Specialist Hospital, Jalingo | Jalingo | Taraba State Specialist Hospital, Jalingo | Department | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1540941039 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TSJ-P-23-00002 | Construction of Roads within Specialist Hospital, Jalingo | Construction of Roads within Specialist Hospital, Jalingo | Jalingo | Taraba State Specialist Hospital, Jalingo | Department | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 325815610 |  | 0 | 0% |  |  | Functional health facilities
SPDO-TSJ-P-23-00003 | Provision of Incinerator for Waste Management Disposal at Specialist Hospital, Jalingo | Provision of Incinerator for Waste Management Disposal at Specialist Hospital, Jalingo | Jalingo | Taraba State Specialist Hospital, Jalingo | Department | Ministry of Health |  |  | Healthcare |  | Good Health and well-being |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TSJ-P-23-00004 | Extension of Power Supply/Rehabilitation/Repairs | Extension of Power Supply/Rehabilitation/Repairs | Jalingo | Taraba State Specialist Hospital, Jalingo | Department | Ministry of Health |  |  | Healthcare |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 180000000 |  | 0 | 0% |  |  | Functional health facilities
SPDO-TSJ-P-23-00005 | Provision of Solar Light within Specialist Hospital, Jalingo | Provision of Solar Light within Specialist Hospital, Jalingo | Jalingo | Taraba State Specialist Hospital, Jalingo | Department | Ministry of Health |  |  | Healthcare |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 120000000 |  | 0 | 0% |  |  | COVID-19 - General
SPDO-TST-P-23-00001 | Renovation of Mechanical Workshop | Renovation of Mechanical Workshop | Jalingo | Taraba State Transport Corporation | Agency | Ministry of Transport and Development |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 79434083 |  | 0 | 0% |  |  | Road - General
SPDO-TST-P-23-00002 | Purchase Workshop Machines and Equipment | Purchase Workshop Machines and Equipment | Jalingo | Taraba State Transport Corporation | Agency | Ministry of Transport and Development |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 80600000 |  | 0 | 0% |  |  | Road - General
SPDO-TST-P-23-00003 | Procurement of 10No. 18-Seater Buses | Procurement of 10No. 18-Seater Buses | Jalingo | Taraba State Transport Corporation | Agency | Ministry of Transport and Development |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Road - General
SPDO-TSU-P-23-00001 | Construction of 2No. Office Building at State University, Jalingo | Construction of 2No. Office Building at State University, Jalingo | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 500000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00002 | Construction of Residential Quarters at TSU, Jalingo | Construction of Residential Quarters at TSU, Jalingo | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00003 | Construction of Sporting Facilities at TSU | Construction of Sporting Facilities at TSU | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 30000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00004 | University Infrastructures Facilities | University Infrastructures Facilities | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 910000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00018 | Revolving Fund for Illiteracy Education in the State | Revolving Fund for Illiteracy Education in the State | Jalingo | Taraba State Mass Education Board | Agency | Ministry of Education |  |  | Education |  | Quality Education |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 5000000 |  | 0 | 0% |  |  | Education sector coordination mechanisms
SPDO-TSU-P-23-00005 | Rehabilitation of Water Facilities | Rehabilitation of Water Facilities | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00006 | Tree Planting and Afforestation | Tree Planting and Afforestation | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Security, Peace, and Unity |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 20000000 |  | 0 | 0% |  |  | Education Not Elsewhere Classified
SPDO-TSU-P-23-00007 | Erosion and Flood Control | Erosion and Flood Control | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Security, Peace, and Unity |  | Climate Action |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 60000000 |  | 0 | 0% |  |  | Education Not Elsewhere Classified
SPDO-TSU-P-23-00008 | Purchase of Motor Vehicle | Purchase of Motor Vehicle | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Security, Peace, and Unity |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 115000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00009 | Purchase of Furniture and Fittings | Purchase of Furniture and Fittings | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 100000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00010 | Purchase of Computers, Printers and Photocopying Machine (TETFund) | Purchase of Computers, Printers and Photocopying Machine (TETFund) | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 110000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00011 | Purchase of Power Generating Plant | Purchase of Power Generating Plant | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 60000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00012 | Purchase of Health and Medical Equipment | Purchase of Health and Medical Equipment | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 70000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00013 | Purchase of Teaching and Learning Aids Equipment | Purchase of Teaching and Learning Aids Equipment | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 105000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00014 | Purchase of Agricultural Equipment | Purchase of Agricultural Equipment | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 150000000 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00015 | Purchase of Surveying Equipment | Purchase of Surveying Equipment | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 49025609 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-TSU-P-23-00016 | Accreditation of 57No. Courses at the State University, Jalingo | To afford the institution with courses recognized by NUC | Jalingo | Taraba State University, Jalingo | Department | Ministry of Education |  |  | Education |  | Quality Education |  | 2023-02-10 | 31/12/2023 | 12 | Completed | 700000000 |  | 700000000 | 100% |  |  | Tertiary institutions’ new courses accreditation
SPDO-UBE-P-23-00001 | UBEC Intervention in Schools Infrastructural Projects | UBEC Intervention in Schools Infrastructural Projects | Jalingo | State Universal Basic Education Board | Agency | Ministry of Education |  |  | Education |  | Industry, Innovation and Infrastructure |  | 2024-01-01 | 2024-12-31 | 52 | Not Started | 1998477207.4 |  | 0 | 0% |  |  | Schools’ infrastructure construction and rehabilitation
SPDO-YDA-P-23-00001 | N500m start-up fund under the youth agency | A dedicated ₦500 million fund under the Youth Agency to provide start-up financing and support for young entrepreneurs, enabling them to establish or expand businesses, create jobs, and promote youth-led economic development across the State. | All LGAs | Youth Development Agency | Agency | HE Office |  |  | Economic and Job Creation |  | Decent Work and Economic Growth |  | 2026-01-04 | 24/08/2026 | 20 | Ongoing | 500000000 |  | 500000000 | 100% |  |  | Societal Re-orientation (General)
Note on F1: Bella: Please, update this field using the drop down

## Sheet1 (hidden)
S/N | PROJECT NAME | PROJECT OBJECTIVE | PROJECT TIMELINE | CURRENT STATUS (% COMPLETED) | TOTAL AMOUNT BUDGETED | AMOUNT SPENT TILL DATE | CHALLENGES ENCOUNTERED
1 | Nyamu-sala model secondary school | to provide a modern conducive learning environment in line with international best practice | September 2023 to march, 2024 | 75% completed | 631219465.87 | 631219465.87 | Lack of enough space within the school for expanded facilities
2 | Comprehensive Secondary School Jalingo ( temporary site) | Renovation and supply of school facilities to provide an alternative accommodation for students exchange program | August to September, 2023 | 100% completed | 48000000 | 48000000 | Some of the machines and equipment of Federal Science and Technical College still left in some buildings needed to be used
3 | Exchange Students program | Transportation and feeding of students exchange program | January to July, 2024 | 35% completed | 175912000 | 164481310 | Inadequate feeding for students ( ₦140.00 per meal × 3 = ₦420.00 per day per student).
4 | Other maintenance services for schools | To provide running Cost for the up-keep of primary and secondary schools in the State | September 2023 to date | On going | 883548000 | 327240000 | Nil
5 | WAEC,NECO & NABTE | To relief parents the burden of the cost of their wards external examinations | December 2023 to June, 2024 | On going | 970136088 | 383655542.75 | Inadequate Data of SS three students in public Schools
6 | BECE & MOCK | To relief parents the burden of the cost of their wards internal examinations | December 2023 to July, 2024 | On going | 234000000 | 26309200 | Nil
7 | Accreditation of courses in COE | To afford the institution with courses recognized by NCCE | October to December, 2023 | 100% completed | 230000000 | 230000000 | Nil
8 | Renovation of TASU hostel | To afford the institution with accommodation for Students | October to December, 2023 | 100% completed | 500000000 | 500000000 | Nil
9 | Accreditation of courses in TSU | To afford the institution with courses recognized by NUC | October to December, 2023 | 100% completed | 700000000 | 700000000 | Nil

## Ministry Weighting
22 MINISTRIES IN TARABA | Weighting
Ministry of Education | 10%
Ministry of Health | 9%
Ministry of Women Affairs & Child Development | 7%
Ministry of Youth & Sports Development | 7%
Ministry of Finance, Budget, and Economic Planning | 5%
Ministry of Works & Infrastructure Development | 5%
Ministry of Commerce, Trade & Industry | 5%
Ministry of Rural & Urban Development | 5%
Ministry of Agriculture & Food Security | 5%
Ministry of Digital Economy & Innovation | 4%
Ministry of Energy and Economic Development | 4%
Ministry of Science & Technology | 4%
Ministry of Transportation Development | 4%
Ministry of Water Management & Aquatic Affairs | 4%
Ministry of Cooperative & Poverty Alleviation | 3%
Ministry of Justice | 3%
Ministry of Heritage & Eco-Tourism | 3%
Ministry of Information and Re-Orientation | 3%
Ministry of Special Duties, Humanitarian Services and Regional Development | 3%
Ministry of Waste Management and Innovation | 3%
Ministry of Environmental and Climate Change | 2%
Ministry Social Justice & Re-Integration | 2%
100%
58

## Sheet2 (hidden)
NAME | PROJECT OBJECTIV | PROJECT TIMELINES | CURRENT STATUS OF COMPLETION | KEY MILESTIONS ACTEVED | TOTAL AMOUNT BUDGETED | ACOUNT SPENT TILL DATE | CHANLLENGES ENLENTERED | ANY OTHER PERNENT INFORMATION
Construction of college of Nursing and Midwifery Jalingo | Training of Human rescues for Health (Nurses and Midwiees | Timely | 55-60% | Most Structures are set up | ₦7,000,000,000.00 | ₦4,000,000,000.00 | Lack of Compensation of some acquired Lands | The NBTE Accreditation will require some special aspects of the project be completed before their visit
2. First Referral Hospital Lissam | Provision of medical Treatments to Patients | Timely | 50%? | Original Completion of abandoned work | ₦2,990,000,000.00 | ₦2,990,000,000.00 | Supervisions not involved at site | Supervisors not involved Ministry not adequately briefed on work progress
3. Purchase of 175 pentacyclic Ambulance | To convey patients to designated Health family | Timely | 0.03 | Proposal submitted 3 initially supplied | 2120823762.5 | ₦20,000,000.00 | Lack of release of fund | Lack of release of fund
4. Purchase of specialized equipment for 3 specialist Hospital | Provision of Specialized Equipment | Timely | Yet | Equipping of hospital | ₦13,594,917,017:00 | Yet | Yet | Yet
5. Purcahse of Drugs and Medicines Hospital Consumables | Treatment of patients | Timely | 1 | Health Facilitation Supplied with modifier | ₦35000000 | ₦35000000 | Seamless | Need for more Medicine
6. Supply of Laboratory equipments and Consumables | Hospital Laboratory for 168 PHCS | Timely | Yet | Equipping 168 PHCS in the State | ₦1,200,00,000.00 | Yet | Yet to provide fund | Yet to be funded
7. Supply of Medicines for 168 PHCS and 168 GH | Treatment of patients | Timely | Yet to commence | Medicines for 168 PHCS and 16 GHS | ₦300,000,000.00 | Yet | Yet to be funded | Fund Yet to be released
8. Supply of Laboratory equipments and Consumables for 168 PHCS and 16 GHS | Hospital Laboratory for the 168 PHCS | Timely | Yet to commence | Lab equipment for 168 PHCS in the State | ₦500,000,000.00 | Yet | Yet | Yet

## LGA Weighting
LGA
Ardo Kola | 6.25%
Bali | 6.25%
Donga | 6.25%
Gashaka | 6.25%
Gassol | 6.25%
Ibi | 6.25%
Jalingo | 6.25%
Karim Lamido | 6.25%
Kurmi | 6.25%
Lau | 6.25%
Sardauna | 6.25%
Takum | 6.25%
Ussa | 6.25%
Wukari | 6.25%
Yorro | 6.25%
Zing | 6.25%
100%

## SDG Weighting
SDGs GOALs | Weighting
No Poverty | 8%
Good Health and Well-being | 8%
Quality Education | 8%
Decent Work and Economic Growth | 8%
Zero Hunger | 7%
Peace, Justice, and Strong Institutions | 7%
Gender Equality | 6%
Clean Water and Sanitation | 6%
Reduced Inequality | 6%
Sustainable Cities and Communities | 6%
Climate Action | 5%
Affordable and Clean Energy | 5%
Industry, Innovation, and Infrastructure | 5%
Responsible Consumption and Production | 5%
Partnerships for the Goals | 4%
Life Below Water | 3%
Life on Land | 3%
100%

## Office of the governors Project (hidden)
Renovation of the Governors Office area
Renovation of The Governors Lodge
Reconstruction of the Banquet Hall
Taraba Aids Control Agency Projects
Reconstruction of the Government House Gates

## MDAs Codes
AGENCY CODE | 22 MINISTRIES IN TARABA | AGENCY CODE | NAME OF MDA
MAG | Ministry of Agriculture & Food Security | SME | Agency for Small & Medium Scale Enterprises
MCT | Ministry of Commerce, Trade & Industry | BLS | Bureau for Land and Survey
MCP | Ministry of Cooperative & Poverty Alleviation | BSM | Bureau for Solid Minerals
MDI | Ministry of Digital Economy & Innovation | BPP | Bureau of Public Procurement (Due Process)
MED | Ministry of Education | CSC | Civil Service Commission (CSC)
MEE | Ministry of Energy and Economy Development | COA | College of Agriculture, Jalingo
MEC | Ministry of Environmental and Climate Change | COE | College of Education, Zing
MFB | Ministry of Finance, Budget, and Economic Planning | COH | College of Health Technology, Takum
MHT | Ministry of Health | CSA | Community & Social Development Agency
MHE | Ministry of Heritage & Eco-Tourism | CCA | Customary Court of Appeal
MIR | Ministry of Information and Re-Orientation | FCP | FADAMA CARES Project Support Unit
MJT | Ministry of Justice | FRC | Fiscal Responsibility Commission
MRU | Ministry of Rural & Urban Development | HCJ | High Court of Justice
MST | Ministry of Science & Technology | HAC | House of Assembly Service Commission
MSS | Ministry of Special Duties & Social Services | IVP | IFAD - VCD Project Support Unit
MTR | Ministry of Transportation Development | LSC | Local Government Service Commission (LGSC)
MWM | Ministry of Waste Management and Innovation | NEP | NEPAD Taraba Coordinating Unit
MWA | Ministry of Water Management & Aquatic Affairs | OEG | Office of the Executive Governor
MWC | Ministry of Women Affairs & Child Development | OPG | Office of the Deputy Governor
MWI | Ministry of Works & Infrastructure Development | HSC | Office of the Head of Service (Career Management)
MYS | Ministry of Youths & Sports Development | HSD | Office of the Head of Service (Manpower Development)
MSJ | Ministry Social Justice & Re-Integration | OSC | Office of the Head of Service (Common Services, IPPS/ICT)
MNP | Ministry of Nursery and Primary Education | OAS | Office of the Auditor General (State)
|  | OAL | Office of the Auditor General (Local Govt. Areas)
|  | OSG | Office of the SGS - General Services
|  | OSH | Office of the SGS - Home Affairs & Special Services
|  | TSB | Taraba State Boundary Commission
|  | SMA | State Emergency Management Agency
|  | TCA | Taraba State Aids Control Agency
|  | TSB | Taraba State Pension Board
|  | TGS | Taraba Geographic Information Systems
|  | TSA | Taraba State House of Assembly
|  | SIE | State Independent Electoral Commission (SIEC)
|  | TAD | Taraba Agricultural Devt. Project (TADP)
|  | THU | Tractor Hiring Unit (THU)
|  | TAP | Taraba Agricultural Produce Marketing Agency
|  | TSI | Taraba State Internal Revenue Service
|  | TST | Taraba State Transport Corporation
|  | TCM | Taraba Commercial Motorcycle & Monitoring Agency
|  | TSC | Taraba State Arts Council
|  | RWA | Rural Water Supply & Sanitation Agency
|  | SCA | Sharia Court of Appeal
|  | TSS | Taraba State Sports Council
|  | UBE | State Universal Basic Education Board
|  | TPH | Taraba State Polytechnic, Suntai
|  | TME | Taraba State Mass Education Board
|  | TSU | Taraba State University, Jalingo
|  | TDP | Taraba State Essential Drugs Programme
|  | THJ | Taraba State Specialist Hospital, Jalingo
|  | PHC | Primary Health Care Development Agency, Jalingo
|  | TSA | Taraba State Contributory Health Insurance Agency
|  | BTS | Taraba State Scholarship Board
|  | TSH | Taraba State Specialist Hospital, Jalingo
|  | SSA | State Sanitation Agency
|  | YDA | Youth Development Agency

## Sheet3
300 sanitation jobs: Created for women and youths in Jalingo within 74 hours of assumption
Teaching Hospital: First time ever Taraba gets a Teaching Hospital
Doctors’ salaries increased (healthcare workers salary increased)
Commencement of payment bonded medical students on salary of GL 5 and GL 7
4. Recruitment of additional 500 Nurses and Midwives by Health Service Management Board | HSMB
Funded matriculations, convocation and accreditation exercises in all the tertiary institutions in the state. | Education
300 sanitation jobs: Created for women and youths in Jalingo within 74 hours of assumption | Sanitation Agency
N500m start-up fund under the youth agency | Youth Agency
Launched: Electronic portal for filing criminal cases in Taraba State High Courts | Justice
Legal Backing: Chief Judge signed Taraba State Civil Procedure Rules 2026 + Practice Direction on e-filing | Justice
Employment of additional 20 lawyers | Justice